## 2016
DELTA STATE PPC FORM: ANNUAL PROCUREMENT PLAN FOR PROCURING ORGANIZATIONS NAME OF PROCURING ORGANISATION: MINISTRY OF BASIC AND SECONDARY EDUCATION
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
S/N | SUB HEAD | PROJECT DESCRIPTION | APPROVED 2016 BUDGET | NAME OF CONTRACTOR | YEAR OF AWARD | EXPECTED DATE OF COMPLETION | CONTRACT SUM | % OF JOB COMPLETION | AMOUNT PAID TO DATE | OUTSTANDING PAYMENT | LGA | PROJECT STATUS
1 | 20(i) | Renovation of Main Workshop and External Automobile Workshop, Issele-Uku Technical College, Issele-Uku, Aniocha North LGA | 8929224198 | Neodede Nig. Ent, No. 5, Abakaliki Close, D.S.C. Complex, Warri. | 2016 | 6 Months after award | 7337761.88 | 100% | 7337761.88 | 0 | Aniocha North | Completed
2 | 20(i) | Construction of 2(Nos.) Prototype Steel Stanchion and Structural Roof Workshop Building, Issele-Uku Technical College, Issele-Uku, Aniocha North LGA | 8929224198 | Runola Nig. Ltd, 13, High Court Road, Okpanam | 2016 | 6 Months after award | 106218857.78 | 100% | 106218857.78 | 0 | Aniocha North | Completed
3 | 20(i) | Procurement of Science Laboratory Furniture and Equipment, Issele-Uku Technical College, Issele-Uku, Aniocha North LGA | 8929224198 | Favour and Praise Nig. Ent. E7, Okwe Housing Estate, Asaba | 2016 | 6 Months after award | 14694960 | 100% | 14694960 | 0 | Aniocha North | Completed
4 | 20(i) | Construction of Library and Renovation of Administrative Blocks, Issele-Uku Technical College, Issele-Uku, Aniocha North LGA | 8929224198 | Peccot Nig. Limited 7, Awodu Lane, off Anwai Road, Asaba | 2016 | 6 Months after award | 25397280.97 | 100% | 19047960.73 | 6349320.24 | Aniocha North | Completed
5 | 20(i) | Renovation of Chemistry Laboratory and construction of 2 bed room staff quarters (1No.), Issele-Uku Technical College, Issele-Uku, Aniocha North LGA | 8929224198 | Pleedage Int'l concept Ltd, plot 3152, Cadastral zone, 706 Ekoro Eruro River St, Maitama, Abuja. | 2016 | 6 Months after award | 20436926.51 | 90% | 8296308.94 | 12140617.57 | Aniocha North | On-going
6 | 369 | Construction of 1 No. 3 classroom block, Azagba Primary Sch, Issele- Azagba, Aniocha North LGA | 8929224198 | Lillivali Ventures, Plot 26 Pitason Estate, Asaba | 2016 | 6 Months after award | 18817633.79 | 100% | 4704408.45 | 14113225.34 | Aniocha North | Completed
7 | 369 | Construction of 1 No. 6 classroom block with toilets and offices, Adams Primary Sch, Issele-Uku, Aniocha North LGA | 8929224198 | Lillivali Ventures, Plot 26 Pitason Estate, Asaba | 2016 | 6 Months after award | 35021147.37 | 100% | 8755286.84 | 26265860.53 | Aniocha North | Completed
8 | 369 | Construction of 1 No. 6 classroom block with toilets and offices at Gbonoza Primary Sch, Onicha-Ugbo, Aniocha North LGA | 8929224198 | Lillivali Ventures, Plot 26 Pitason Estate, Asaba | 2016 | 6 Months after award | 35021147.37 | 100% | 8755296.84 | 26265850.53 | Aniocha North | Completed
9 | 375 | Supply of Students Desks and Teachers Tables and Chairs at Obomkpa Mixed Sec Sch Obomkpa, Aniocha North LGA | 8929224198 | Lillivali Ventures, Plot 26 Pitason Estate, Asaba | 2016 | 6 Months after award | 10000000 | 100% | 0 | 10000000 | Aniocha North | Completed
10 | 375 | Construction of 1No. 6 classroom block with toilets and offices at Ngwu Mixed Secondary School, Ogwashi-Uku, Aniocha South LGA | 8929224198 | Blue Symphony Investment Limited, No.11 Orbit Estate Port-Harcourt. | 2016 | 6 Months after award | 35021147.37 | 100% | 8755786.84 | 26265360.53 | Aniocha South | Completed
11 | 378 | Construction of 1Nos.3 classroom block with toilets and offices at Ngwu Mixed Secondary School, Ogwashi - Uku, Aniocha South LGA | 8929224198 | Serock Energy Services Limited, House 14, Plot 38, Jaiye Oyedotun Street, Magodo-Ikeja. | 2016 | 6 Months after award | 18817633.79 | 100% | 4704408.45 | 14113225.34 | Aniocha South | Completed
12 | 378 | Supply of 1,029 Students and 119 Teachers furniture to Selected Schools, Aniocha South LGA | 8929224198 | Blue Symphony Investment Limited, No.11 Orbit Estate Port-Harcourt. | 2016 | 6 Months after award | 46161218.84 | 100% | 11540304.71 | 34620914.13 | Aniocha South | Completed
13 | 265 | Renovation of Six Classroom Block with Stores and Toilets at Comprehensive Secondary School, Ogwashi-Uku, Aniocha South LGA | 8929224198 | Chudigwe Global Ventures, No.1 Pascal Adigwe Lane, off DBS Road, Asaba. | 2016 | 6 Months after award | 19290500 | 100% | 18325975 | 964525 | Aniocha South | Completed
14 | 265 | Supply of Students’ 100 and 15 Teachers’ Furniture to Comprehensive Secondary School, Ogwashi-Uku, Aniocha South LGA | 8929224198 | Chu-Emma Global Services, No.77 Imudia Street, Agbor. | 2016 | 6 Months after award | 4715500 | 100% | 1178875 | 3536625 | Aniocha South | Completed
15 | 375 | Supply of Students Desks and Teachers Tables and Chairs to Selected Schools, Bomadi LGA | 8929224198 | Tijo Concept Services Ltd, No. 7 Akassa Street Ebiogbo Qtrs, Kpakiama Town | 2016 | 6 Months after award | 110000000 | 100% | 110000000 | 0 | Bomadi | Completed
16 | 381 | Supply of Students Desks and Teachers Tables and Chairs to Selected Schools, Burutu I | 8929224198 | Ogbein Ventures, No. 3 Donowari Qtrs, Okpokunou. | 2016 | 6 Months after award | 100000000 | 100% | 80000000 | 20000000 | Burutu | Completed
17 | 380 | Supply of Students Desks and Teachers Tables and Chairs to Selected Schools, Burutu II | 8929224198 | Dan- Mic Enterprises, No. 300 Obi Ikechukwu Road, Agbor | 2016 | 6 Months after award | 100000000 | 100% | 100000000 | 0 | Burutu | Completed
18 | 382 | Construction of 1No 3 Classroom Block with Toilets and Offices at Staff Secondary School, Eku, Baptist Government Hospital, Ethiope East LGA | 8929224198 | Neodede Nigeria Enterprises, No.5 Abakaliki Close DSC Complex, Warri | 2016 | 6 Months after award | 18817633.79 | 100% | 10000000 | 8817633.79 | Ethiope East | Completed
19 | 380 | Construction of 1No. 6 Classroom Block with Toilets and Offices at Ebenezer Primary School, Erho-Abraka, Ethiope East LGA | 8929224198 | Neodede Nigeria Enterprises, No.5 Abakaliki Close DSC Complex, Warri | 2016 | 6 Months after award | 35021147.37 | 100% | 35021147.37 | 0 | Ethiope East | Completed
20 | 382 | Supply of 1,029 Students’ Desks and 119 Teachers’ furniture to Selected Schools, Ethiope East LGA | 8929224198 | Neodede Nigeria Enterprises, No.5 Abakaliki Close DSC Complex, Warri | 2016 | 6 Months after award | 46162218.84 | 100% | 46162218.84 | 0 | Ethiope East | Completed
21 | 488 | Renovation of 2No.6 Classroom Blocks (A) at Onyobru Secondary School, Onyobru-Jesse, Ethiope West LGA | 8929224198 | Emimarvis Global Resources, No.22 Redeemer Street, Asaba. | 2016 | 6 Months after award | 27581503.51 | 100% | 6895375.88 | 20686127.63 | Ethiope West | Completed
22 | 488 | Renovation of 2No.6 Classroom Blocks (B) at Onyobru Secondary School, Onyobru-Jesse, Ethiope West LGA | 8929224198 | Emimarvis Global Resources, No.22 Redeemer Street, Asaba. | 2016 | 6 Months after award | 27581503.51 | 100% | 6895375.88 | 20686127.63 | Ethiope West | Completed
23 | 488 | Reconstruction/ Renovation of 2No.6 Classroom Blocks (A) with Offices and Toilets at Oreki Secondary School, Oghareki, Ethiope West LGA | 8929224198 | Rizim Resources, No.12 Chike St. West-End Asaba. | 2016 | 6 Months after award | 25256685.87 | 100% | 23986625.7 | 1270060.17 | Ethiope West | Completed
24 | 488 | Reconstruction/ Renovation of 2No.6 Classroom Blocks (B) with Offices and Toilets at Oreki Secondary School, Oghareki, Ethiope West LGA | 8929224198 | Obafua Nigeria Limited, Km 18 Asaba-Benin Express Way, Asaba. | 2016 | 6 Months after award | 25256685.87 | 100% | 23986625.7 | 1270060.17 | Ethiope West | Completed
25 | 488 | Reconstruction/ Renovation of 2No.6 Classroom Blocks (A) with Offices and Toilets at Ukavbe Secondary School, Otefe-Oghara, Ethiope West LGA | 8929224198 | Omitelojor Ventures, o.22 Redeemers Street, off Marian Babangida Road,Asaba. | 2016 | 6 Months after award | 27350342.71 | 100% | 24615308.44 | 2735034.27 | Ethiope West | Completed
26 | 488 | Reconstruction/ Renovation of 2No.6 Classroom Blocks (B) with Offices and Toilets at Ukavbe Secondary School, Otefe-Oghara, Ethiope West LGA | 8929224198 | Omitelojor Ventures, No.22 Redeemers Street, off Marian Babangida Road,Asaba. | 2016 | 6 Months after award | 27350342.71 | 100% | 26120336.51 | 1230006.2 | Ethiope West | Completed
27 | 488 | Supply of 250 Students’ Desks and 50 Teachers’ furniture to Selected Schools, Ethiope West LGA | 8929224198 | Blue Breed Integrated Services, No.1139 Bishop Oluwole Street, Victoria Island. | 2016 | 6 Months after award | 12305000 | 100% | 12305000 | 0 | Ethiope West | Completed
28 | 488 | Renovation of 2No.6 Classroom Blocks (A) with Offices and Toilets at Ighoyota Secondary School, Ugbokpa-Mosogar, Ethiope West LGA | 8929224198 | Obafua Nigeria Limited, Km 18 Asaba-Benin Express Way, Asaba. | 2016 | 6 Months after award | 24846788.23 | 100% | 22063366.41 | 2783421.82 | Ethiope West | Completed
29 | 488 | Renovation of 2No.6 Classroom Blocks (B) with Offices and Toilets at Ighoyota Secondary School, Ugbokpa-Mosogar, Ethiope West LGA | 8929224198 | Obafua Nigeria Limited, Km 18 Asaba-Benin Express Way, Asaba. | 2016 | 6 Months after award | 24846788.23 | 100% | 22063362.47 | 2783425.76 | Ethiope West | Completed
30 | 375 | Supply of Students Desks and Teachers Tables and Chairs to Selected Schools, Ethiope West LGA | 8929224198 | Blu Breed Integrated Services, No. 1139 Bishop Oluwole Street, Victoria Island, Lagos | 2016 | 6 Months after award | 100000000 | 100% | 100000000 | 0 | Ethiope West | Completed
31 | 384 | Supply of 2,058 Students and 386 Teachers furniture to Selected Schools, Ika North East LGA | 8929224198 | Kenlly Ugbebor Ventures, No.42 Owanta Street, Boji-Boji, Agbor. | 2016 | 6 Months after award | 100000000 | 100% | 100000000 | 0 | Ika North East | Completed
32 | 277 | Supply of 400 Students’ including 60 Teachers’ Tables and Chairs to Owa-Alero Secondary School, Owa-Alero, Ika North East LGA | 8929224198 | Pet-Uzor Nigeria Enterprises, No.199 Warri/Sapele Road, Warri. | 2016 | 6 Months after award | 14633670 | 100% | 14633670 | 0 | Ika North East | Completed
33 | 227 | Renovation of 1No. 6 classroom block with attached Offices and Toilets at Otolokpo Mixed Secondary School, Otolokpo, Ika North East LGA | 8929224198 | Nimbiri Ventures, No.30 Orubor Street, Agbor. | 2016 | 6 Months after award | 16600572.67 | 100% | 16600572.67 | 0 | Ika North East | Completed
34 | 227 | Renovation of 1No. 3 classroom Science Laboratory Block with attached Offices and Toilets at Otolokpo Mixed Secondary School, Otolokpo, Ika North-East LGA | 8929224198 | Stitches and Fabrics Enterprises, No.2B Agada Close, Military Housing Estate, Kurudu | 2016 | 6 Months after award | 15031680.33 | 100% | 13972523.33 | 1059157 | Ika North East | Completed
35 | 227 | Supply of 111 Students’ Desks and 45 Teachers’ Furnitures to Otolokpo Mixed Secondary School, Otolokpo, Ika North-East LGA | 8929224198 | Chu-Emma Global Ventures, No.77 Imudia Street, Agbor. | 2016 | 6 Months after award | 6354480.008 | 100% | 6354480.01 | 0 | Ika North East | Completed
36 | 75 | Completion/ Rehabilitation of Science Laboratory Block at Akumazi Grammar School, Akumazi-Umuocha, Ika North East LGA | 8929224198 | Othereez Nigeria Enterprises, Plot 654, 15th Street DDPA Estate Warri. | 2016 | 6 Months after award | 13049821.19 | 100% | 12397330.13 | 652491.06 | Ika North East | Completed
37 | 75 | Demolition/ Reconstruction of Administrative Block at Akumazi Grammar School, Akumazi-Umuocha, Ika North East LGA | 8929224198 | Othereez Nigeria Enterprises, Plot 654, 15th Street DDPA Estate Warri. | 2016 | 6 Months after award | 21763678.87 | 100% | 20675494.93 | 1088183.94 | Ika North East | Completed
38 | 75 | Electricity connection to BEDC at Akumazi Grammar School, Akumazi-Umuocha, Ika North East LGA | 8929224198 | Othereez Nigeria Enterprises, Plot 654, 15th Street DDPA Estate Warri. | 2016 | 6 Months after award | 1186499.94 | 100% | 1186499.94 | 0 | Ika North East | Completed
39 | 20(i) | Landscaping and Erosion Control Work (Phase I), Construction of Football Field, Sport Pavilion and Perimeter Block Wall Fence to demarcate Alibuba Primary school in Agbor Technical College, Agbor, Ika South LGA | 8929224198 | Runola Nig. Ltd, 13, High Court Road, Okpanam | 2016 | 6 Months after award | 99993193.17 | 100% | 99993193.17 | 0 | Ika South | Completed
40 |  | Construction of water borehole, Students/Teachers Toilets, Electricity Connection to BEDC Mains at Alibuba Primary School, Agbor, Ika South LGA | 8929224198 | Runola Nig. Ltd, 13, High Court Road, Okpanam | 2016 | 6 Months after award | 10500000 | 100% | 10500000 | 0 | Ika South | Completed
41 | 20(i) | Provision and Installation of 1No. 45KVA Sound Proof Generator Set at Agbor Technical College, Agbor, Ika South LGA | 8929224198 | Nimbiri Ventures, 30 Orubor Street, Agbor. | 2016 | 6 Months after award | 7602119.47 | 100% | 7602119.47 | 0 | Ika South | Completed
42 |  | Construction of 1No.6 classroom block at Aliohen Primary School, Aliohen, Abavo, Ika South LGA | 8929224198 | Austinmoore Enterprises, No.11 Owa-Ekei Road, Boji-Boji, Owa | 2016 | 6 Months after award | 35021147.37 | 100% | 29802353.44 | 5218793.93 | Ika South | Completed
43 |  | Supply of 1,680 Students and 185 Teachers furniture to Selected Schools, Ika South LGA | 8929224198 | Austinmoore Enterprises, No.11 Owa-Ekei Road, Boji-Boji, Owa | 2016 | 6 Months after award | 74978852.63 | 100% | 74978852.63 | 0 | Ika South | Completed
44 | 365 | Renovation of 1No.3 Classroom Blocks with Stores and Toilets at Alisimie Mixed Secondary School, Alisimie | 8929224198 | Antoblue Energy Limited, DDPA Housing Estate, Asaba | 2016 | 6 Months after award | 8535208.07 | 100% | 7794913.44 | 740294.63 | Ika South | Completed
45 | 365 | Construction of Water Borehole at Alisimie Mixed Secondary School, Alisimie | 8929224198 | Antoblue Energy Limited, DDPA Housing Estate, Asaba | 2016 | 6 Months after award | 1770299.91 | 100% | 1184400 | 585899.91 | Ika South | Completed
46 | 365 | Electricity connection to BEDC mains at Alisimie Mixed Secondary School, Alisimie | 8929224198 | Antoblue Energy Limited, DDPA Housing Estate, Asaba | 2016 | 6 Months after award | 1186499.94 | 100% | 1186499.94 | 0 | Ika South | Completed
47 | 365 | Renovation of 1No.6 Classroom Blocks with Stores and Toilets, Administrative and Chemistry/Physics Laboratory at Alisimie Mixed Secondary School, Alisimie | 8929224198 | Nuvano Atlas Limited, No.114 Obafemi Awolowo Way, Ikeja | 2016 | 6 Months after award | 11101071.07 | 100% | 11101071.07 | 0 | Ika South | Completed
48 | 365 | Supply of 100 Students Desks and 20 Teachers Tables and Chairs to Alisimie Mixed Secondary School, Alisimie | 8929224198 | Nuvano Atlas Limited, No.114 Obafemi Awolowo Way, Ikeja | 2016 | 6 Months after award | 4406920.14 | 100% | 4406920.14 | 0 | Ika South | Completed
49 | 365 | Construction of Science Laboratory Building at Alidinma Secondary School, Agbor-Alidinma | 8929224198 | Rizim Resources, No.12 Chike St. West-End Asaba | 2016 | 6 Months after award | 22368238.13 | 100% | 20987982.99 | 1380255.14 | Ika South | Completed
50 | 365 | Demolition of old 1No.3 Classroom Block and Re-construction of 1No.3 Classroom Block with 4N0. Attached offices at Alidinma Secondary School, Agbor-Alidinma, Ika South LGA | 8929224198 | Rizim Resources, No.12 Chike St. West-End Asaba | 2016 | 6 Months after award | 13607526.82 | 100% | 12807352.23 | 800174.59 | Ika South | Completed
51 | 365 | Construction of Students/Teachers Toilet at Alidinma Secondary School, Agbor-Alidinma, Ika South LGA | 8929224198 | Rizim Resources, No.12 Chike St. West-End Asaba | 2016 | 6 Months after award | 4067435.02 | 100% | 3864063.27 | 203371.75 | Ika South | Completed
52 | 365 | Construction of Water Borehole at Alidinma Secondary School, Agbor-Alidinma, Ika South LGA | 8929224198 | Rizim Resources, No.12 Chike St. West-End Asaba | 2016 | 6 Months after award | 1770290.91 | 100% | 1586549.18 | 183741.73 | Ika South | Completed
53 | 365 | Electricity Connection to BEDC Mains at Alidinma Secondary School, Agbor-Alidinma, Ika South LGA | 8929224198 | Rizim Resources, No.12 Chike St. West-End Asaba | 2016 | 6 Months after award | 1186499.94 | 100% | 1186499.94 | 0 | Ika South | Completed
54 | 190 | Renovation of T-Shaped Examination Hall with attached Staff Quarters at Ekuku-Agbor Grammar School, Ekuku-Agbor, Ika South LGA | 8929224198 | Neodede Nigeria Enterprises,No.5 Abakaliki Close DSC Complex, Warri. | 2016 | 6 Months after award | 22401918 | 100% | 19877886.5 | 2524031.5 | Ika South | Completed
55 | 190 | Renovation of 1No. 6 classroom block with attached Offices and Toilets at Ekuku-Agbor Grammar School, Ekuku-Agbor, Ika South LGA | 8929224198 | Neodede Nigeria Enterprises, No.5 Abakaliki Close DSC Complex, Warri. | 2016 | 6 Months after award | 19478783 | 60% | 4869695.75 | 14609087.25 | Ika South | Completed
56 | 190 | Renovation of 1No.4 Classroom Blocks with attached Offices and Toilets at Ekuku-Agbor Grammar School, Ekuku-Agbor, Ika South LGA | 8929224198 | Neodede Nigeria Enterprises, No.5 Abakaliki Close DSC Complex, Warri. | 2016 | 6 Months after award | 21016044 | 100% | 18440143 | 2575901 | Ika South | Completed
57 | 190 | Supply of 175 Students’ Desk and 49 Teachers’ Tables and Chairs to Ekuku-Agbor Grammar School, Ekuku-Agbor, Ika South LGA | 8929224198 | Neodede Nigeria Enterprises,No.5 Abakaliki Close DSC Complex,Warri. | 2016 | 6 Months after award | 9344075 | 100% | 9344075 | 0 | Ika South | Completed
58 | 20(i) | Provision and Installation of 1No. 45KVA Sound Proof Generator Set and Purchase of Materials/Construction of 22Nos. Span of Low Tension Power Distribution Network at Ofagbe Technical College, Ofagbe, Isoko North LGA | 8929224198 | Peacealex Enterprises, 32, Summit Road, Asaba | 2016 | 6 Months after award | 10397880.53 | 100% | 10397880.53 | 0 | Isoko North | Completed
59 | 385 | Construction of 2 Nos. 6 classroom block with toilets and offices at Akiewhe Secondary School, Akiewhe, Isoko North LGA | 8929224198 | Guwe-T Resources Limited, House of Assembly Complex, Asaba. | 2016 | 6 Months after award | 70042294.74 | 100% | 70042294.74 | 0 | Isoko North | Completed
60 | 385 | Supply of 1,080 Students and 153 Teachers furniture to Selected Secondary Schools, Isoko North LGA | 8929224198 | Guwe-T Resources Limited, House of Assembly Complex, Asaba. | 2016 | 6 Months after award | 49957705.26 | 100% | 49957705.26 | 0 | Isoko North | Completed
61 | 384 | Supply of 2,058 Students and 386 Teachers furniture to Selected Secondary Schools, Isoko South I | 8929224198 | Emimarvis Global Resource, No.22 Redeemer Street, Asaba. | 2016 | 6 Months after award | 100000000 | 100% | 95000000 | 5000000 | Isoko South | Completed
62 | 373 | Supply of Students Desks and Teachers Tables and Chairs to Selected Schools, Isoko South II | 8929224198 | Omitelojor Ventures, No. 22 Redeemers Street, off Marian Babangida Road, Asaba. | 2016 | 6 Months after award | 100000000 | 100% | 95000000 | 5000000 | Isoko South | Completed
63 | 487 | Construction of 1 No. 6 classroom block with toilets and offices at Aboh Grammar School, Abor, Ndokwa East LGA | 8929224198 | Mathnebi Nigeria Limited, No. 28 Emekuku St D/Line, Port- Harcourt | 2016 | 6 Months after award | 35021147.37 | 100% | 31367090 | 3654057.37 | Ndokwa East | Completed
64 | 487 | Construction of 1 No. 6 classroom block with toilets and offices at Mixed Secondary School, Okpai-Oluchi, Ndokwa East LGA | 8929224198 | Mathnebi Nigeria Limited, No. 28 Emekuku St D/Line, Port- Harcourt | 2016 | 6 Months after award | 35021147.37 | 100% | 30137095 | 4884052.37 | Ndokwa East | Completed
65 | 487 | Construction of 1 No. 6 classroom block with toilets and offices at Niger Primary School, Asaba- Ase, Ndokwa East LGA | 8929224198 | Mathnebi Nigeria Limited, No. 28 Emekuku St D/Line, Port- Harcourt | 2016 | 6 Months after award | 35021147.37 | 100% | 8755286.64 | 26265860.73 | Ndokwa East | Completed
66 | 487 | Supply of Students Desks and Teachers Tables and Chairs to Selected Schools, Ndokwa East LGA | 8929224198 | Mathnebi Nigeria Limited, No. 28 Emekuku St D/Line, Port- Harcourt | 2016 | 6 Months after award | 42000000 | 100% | 10500000 | 31500000 | Ndokwa East | Completed
67 | 20(i) | Completion of Prototype Steel Stanchion and Structural Roof Workshop Building (Electrical Workshop/Classroom) at Utagba-Ogbe Technical College, Kwale, Ndokwa West LGA | 8929224198 | Yowa Global Services, 140, Airport Road, Warri. | 2016 | 6 Months after award | 32331216.73 | 100% | 32331216.73 | 0 | Ndokwa West | Completed
68 | 20(i) | Completion of Staff Quarters at Utagba-Ogbe Technical College, Kwale, Ndokwa West LGA | 8929224198 | Valnobis Global Ventures Nig. Ltd, plot 38, R.F. Ovwigho Drive, Core Area, Asaba | 2016 | 6 Months after award | 5519723.72 | 100% | 5519723.72 | 0 | Ndokwa West | Completed
69 | 20(i) | Renovation/Completion of 1No. Six (6) Classroom Block at Utagba-Ogbe Technical College, Kwale, Ndokwa West LGA | 8929224198 | Chino Global Ventures 77, Imudia Street, Agbor | 2016 | 6 Months after award | 14733977.26 | 100% | 14733977.26 | 0 | Ndokwa West | Completed
70 | 20(i) | Demolition and Construction of Male Hostel Block at Utagba-Ogbe Technical College, Kwale, Ndokwa West LGA | 8929224198 | Jitobs Ltd, opp. Old Secretariate, Asaba | 2016 | 6 Months after award | 47720901.25 | 100% | 41957063.47 | 5763837.78 | Ndokwa West | Completed
71 | 20(i) | Construction of Laboratory Block of 3Nos Halls, Offices and Toilets at Utagba-Ogbe Technical College, Kwale, Ndokwa West LGA | 8929224198 | Soloak Nig. Ltd. 10, Idise Dafe Street, Hospital Quarters, GRA. Obiaruku | 2016 | 6 Months after award | 16877213.14 | 100% | 16877213.14 | 0 | Ndokwa West | Completed
72 | 20(i) | Renovation of Dining/Kitchen and the Renovation of Generator House at Utagba-Ogbe Technical College, Kwale, Ndokwa West LGA | 8929224198 | Lemoh Associates Ltd 12, Summit Rd, Asaba | 2016 | 6 Months after award | 25972256.21 | 100% | 25865331.21 | 106925 | Ndokwa West | Completed
73 | 377 | Supply of 470 Teachers' furniture to Selected Schools, Ndokwa West LGA | 8929224198 | Danike Global Resources Ventures, No. 71 Textile Mill Road, Benin City. | 2016 | 6 Months after award | 24322500 | 100% | 6080025 | 18242475 | Ndokwa West | Completed
74 | 377 | Construction of 1 No. 3 classroom block at Emu Primary School, Emu- Uno, Ndokwa West LGA | 8929224198 | Danike Global Resources Ventures, No. 71 Textile Mill Road, Benin City. | 2016 | 6 Months after award | 18817633.79 | 100% | 12818425.89 | 5999207.9 | Ndokwa West | Completed
75 | 377 | Construction of 1 No. 3 classroom block at Amoji Primary School, Amoji, Onicha-Ukwuani, Ndokwa West LGA | 8929224198 | Danike Global Resources Ventures, No. 71 Textile Mill Road, Benin City. | 2016 | 6 Months after award | 18817633.79 | 100% | 17612609.34 | 1205024.45 | Ndokwa West | Completed
76 | 377 | Construction of 1 No. 3 classroom block at Utue Grammar School, Utue- Ogume, Ndokwa West LGA | 8929224198 | Danike Global Resources Ventures, No. 71 Textile Mill Road, Benin City. | 2016 | 6 Months after award | 18817633.79 | 100% | 17876752.1 | 940881.69 | Ndokwa West | Completed
77 | 377 | Construction of 1 No. 3 classroom block at Abbi Girls Grammar School, Abbi, Ndokwa West LGA | 8929224198 | Danike Global Resources Ventures, No. 71 Textile Mill Road, Benin City. | 2016 | 6 Months after award | 18817633.79 | 100% | 17582684.34 | 1234949.45 | Ndokwa West | Completed
78 | 372 | Construction of 1Nos.3 classroom block with toilets and offices at Osubi Secondary School, Osubi, Okpe LGA | 8929224198 | Onejire and Sons Nigeria Limited, NO.44 Awhinawhi Road, Ughelli. | 2016 | 6 Months after award | 18817633.79 | 100% | 17361140.5 | 1456493.29 | Okpe | Completed
79 | 372 | Construction of 2 Nos.6 classroom block with toilets and offices at Osubi Secondary School, Osubi, Okpe LGA | 8929224198 | Onejire and Sons Nigeria Limited, NO.44 Awhinawhi Road, Ughelli. | 2016 | 6 Months after award | 70042294.74 | 100% | 22295081.69 | 47747213.05 | Okpe | Completed
80 | 373 | Supply of 232 Students and 41 Teachers furniture to Selected Secondary Schools, Okpe LGA | 8929224198 | Onejire and Sons Nigeria Limited, NO.44 Awhinawhi Road, Ughelli. | 2016 | 6 Months after award | 11140071.47 | 100% | 11140071.47 | 0 | Okpe | Completed
81 | 122 | Construction of 1No.6 Classroom Block with Stores and Toilets at Okwegume Secondary School, Okwegume, Okpe LGA | 8929224198 | Rizim Resources, No.12 Chike St. West-End Asaba. | 2016 | 6 Months after award | 34021147.37 | 100% | 31097638.2 | 2923509.17 | Okpe | Completed
82 | 122 | Supply of 112 Students’ Desks and 12 Teachers furniture to Okwegume Secondary School, Okwegume, Okpe LGA | 8929224198 | Bifo John and Company, No.3 Ogbofobo Crescent West-End, Asaba. | 2016 | 6 Months after award | 4978852.63 | 100% | 4978852.63 | 0 | Okpe | Completed
83 | 388 | Supply of 2,315 Students and 386 Teachers furniture to Selected Schools, Oshimili North LGA | 8929224198 | Tunjila Corperate Services, NO. 14 dbs Road, Asaba. | 2016 | 6 Months after award | 110000000 | 100% | 110000000 | 0 | Oshimili North | Completed
84 |  | Demolition of the Multi-Purposed Hall at Delta State Vocational Education Centre, Asaba, Oshimili South LGA | 8929224198 | Favour and Praise Nig. Ent. E7, Okwe Housing Estate, Asaba | 2016 | 6 Months after award | 1957514.9 | 100% | 1957514.9 | 0 | Oshimili South | Completed
85 | 375 | Supply of 2,058 Students and 386 Teachers furniture to Selected Secondary Schools, Oshimili South LGA | 8929224198 | Mico Resources, No. 29 Ibusa Road, Asaba. | 2016 | 6 Months after award | 100000000 | 100% | 100000000 | 0 | Oshimili South | Completed
86 | 489 | Construction of 2No.6 Classroom Blocks ‘‘A’’ with Offices and Toilets at Government Model Secondary School, GRA-Asaba, Oshimili South LGA | 8929224198 | Femmak and Company, No.24B Memeh Street Boji-Boji, Owa. | 2016 | 6 Months after award | 31093125 | 100% | 31093125 | 0 | Oshimili South | Completed
87 | 489 | Construction of 2No.6 Classroom Blocks ‘‘B’’ with Offices and Toilets at Government Model Secondary School, GRA-Asaba, Oshimili South LGA | 8929224198 | Rizim Resources, No.12 Chike St. West-End, Asaba. | 2016 | 6 Months after award | 31093125 | 100% | 31093125 | 0 | Oshimili South | Completed
88 | 489 | Construction of Laboratory Blocks with Stores, Offices and Toilets, Oshimili South LGA | 8929224198 | Rizim Resources, No.12 Chike St. West-End, Asaba. | 2016 | 6 Months after award | 19616148.58 | 100% | 19616148.58 | 0 | Oshimili South | Completed
89 | 489 | Construction of Sports Pavilion at Government Model Secondary School, GRA-Asaba, Oshimili South LGA | 8929224198 | Sam Igumbor Enterprises, No.106 Mariere Street, Agbor. | 2016 | 6 Months after award | 19641029.6 | 100% | 19641029.6 | 0 | Oshimili South | Completed
90 | 370 | Supply of Students Desks and Teachers Tables and Chairs to Selected Schools, Patani LGA | 8929224198 | Mebley & Associates Ltd, No. 5 Patani Lane off NTA Road, Asaba | 2016 | 6 Months after award | 100000000 | 100% | 100000000 | 0 | Patani | Completed
91 | 20(i) | Additional Works (Renovation of 18Nos. Boys Quarters) at Sapele Technical College, Sapele | 8929224198 | Blue Pearls Global Link Ltd, 18, DDPA Housing Estate, Asaba. | 2016 | 6 Months after award | 70200000 | 100% | 70200000 | 0 | Sapele | Completed
92 | 371 | Construction of 1 No. 6 classroom block with toilets and offices at Ovwore Primary School, Ibada, Amukpe, Sapele | 8929224198 | Mooving Nigeria Enterprises, No. 73 Akintola Road, Sapele | 2016 | 6 Months after award | 35021147.37 | 100% | 8755286.84 | 26265860.53 | Sapele | Completed
93 | 371 | Construction of 1 No.6 classroom block with toilets and offices at Ibada-Elume Grammar School, Elume, Ibada-Elume, Sapele | 8929224198 | Mooving Nigeria Enterprises, No. 73 Akintola Road, Sapele | 2016 | 6 Months after award | 35021147.37 | 100% | 8755286.84 | 26265860.53 | Sapele | Completed
94 | 371 | Supply of 2,572 Students and 578 Teachers furniture to Selected Schools, Sapele | 8929224198 | Mooving Nigeria Enterprises, No. 73 Akintola Road, Sapele | 2016 | 6 Months after award | 129957705 | 100% | 129957705 | 0 | Sapele | Completed
95 | 389 | Construction of 1 No. 6 classroom block with toilets and offices at Aladja Secondary School, Aladja, Udu LGA | 8929224198 | Kokobond International Concept Limited, No. 3 Oteboo Hall, Orhuwhorun. | 2016 | 6 Months after award | 35021147.37 | 100% | 32594215 | 2426932.37 | Udu | Completed
96 | 389 | Construction of 1 No. 6 classroom block with toilets and offices at Orhuwhorun High School, Orhuwhorun, Udu LGA | 8929224198 | Kokobond International Concept Limited, No. 3 Oteboo Hall, Orhuwhorun. | 2016 | 6 Months after award | 35021147.37 | 100% | 32594215 | 2426932.37 | Udu | Completed
97 | 5 | Supply of 93 Students’ Desks and 45 Teachers’ Furniture to Ubogu Secondary School, Udu LGA | 8929224198 | Chioino Global Ventures, No.77 Imudia Street, Agbor | 2016 | 6 Months after award | 5215062 | 100% | 5215062 | 0 | Udu | Completed
98 | 20(i) | Renovation of 1No. Six (6) Classrooms Block with Six (6) Offices and four (4) Toilets at Ogor Technical College, Otor-Ogor, Ughelli North LGA | 8929224198 | Donoware Ventures, 18, Apala Street, Warri | 2016 | 6 Months after award | 17472381.93 | 100% | 17472381.93 | 0 | Ughelli North | Completed
99 | 20(i) | Renovation of four (4) Bedroom flat Principals Quarters and renovation/rehabilitation of examination hall at Ogor Technical College, Otor-Ogor, Ughelli North LGA | 8929224198 | EricKings Ventures, 150, Old Lagos/Asaba Road, Agbor. | 2016 | 6 Months after award | 13397253.02 | 100% | 13397253.02 | 0 | Ughelli North | Completed
100 | 20(i) | Construction Administrative Block at Ogor Technical College, Otor-Ogor, Ughelli North LGA | 8929224198 | Anuka and Co. Int Enterprises Ltd, No 6 Ukwerere, DDPA Effurun | 2016 | 6 Months after award | 14541375.78 | 100% | 14541375.78 | 0 | Ughelli North | Completed
101 | 20(i) | Construction of 1No. Prototype Steel Stanchion and Structural Roof Workshop Building at Ogor Technical College, Otor-Ogor, Ughelli North LGA | 8929224198 | DNO Engineering Consultants, 73, Ibusa Road, Asaba | 2016 | 6 Months after award | 44520887.14 | 95% | 11130221.79 | 33390665.35 | Ughelli North | On-going
102 | 20(i) | Construction of Science Laboratory Block at Ogor Technical College, Otor-Ogor, Ughelli North LGA | 8929224198 | DNO Engineering Consultants, 73, Ibusa Road, Asaba | 2016 | 6 Months after award | 24766663.77 | 100% | 24766663.77 | 0 | Ughelli North | Completed
103 | 20(i) | Renovation of six (6) classrooms Block with 6 offices and 4 toilets at Ogor Technical College, Otor-Ogor, Ughelli North LGA | 8929224198 | Pat-Gone Ent. 1&3 Eyesan Street, Warri | 2016 | 6 Months after award | 17472381.94 | 100% | 17472381.94 | 0 | Ughelli North | Completed
104 | 391 | Construction of 1 No. 6 classroom block with toilets and offices at Iyeye Primary School, Edjekota-Ogor, Ughelli North LGA | 8929224198 | De-Mustard Seed System Services, No. 2 Infant Jesus Academy Road, Asaba. | 2016 | 6 Months after award | 35021147.37 | 100% | 20713413.14 | 14307734.23 | Ughelli North | Completed
105 | 390 | Construction of 1Nos.6 classroom block with toilets and offices at Ufuoma Secondary School, Ufuoma, Ughelli North LGA | 8929224198 | Onejire and Sons Nigeria Limited, NO.44 Awhinawhi Road, Ughelli. | 2016 | 6 Months after award | 35021147.37 | 100% | 8755286.84 | 26265860.53 | Ughelli North | Completed
106 | 391 | Construction of 1Nos.6 classroom block with toilets and offices at Oharisi Secondary School, Ughelli North LGA | 8929224198 | Danike Global Resources Ventures, No. 71 Textile Mill Road, Benin City. | 2016 | 6 Months after award | 35021147.37 | 100% | 8755286.84 | 26265860.53 | Ughelli North | Completed
107 | 5 | Supply of 93 Students’ Desks and 45 Teachers’ Furniture to Girls Model Secondary School, Evwreni, Ughelli North LGA | 8929224198 | Chu-Emma Global Ventures, No.77 Imudia Street, Agbor. | 2016 | 6 Months after award | 5215062 | 100% | 5215062 | 0 | Ughelli North | Completed
108 | 390 | Supply of 1,440 Students and 173 Teachers furniture to Selected Schools, Ughelli North I | 8929224198 | Onejire and Sons Nigeria Limited, NO.44 Awhinawhi Road, Ughelli. | 2016 | 6 Months after award | 64978852.63 | 100% | 64978852.63 | 0 | Ughelli North | Completed
109 | 391 | Supply of 590 Students and 135 Teachers furniture to Selected Schools, Ughelli North II | 8929224198 | Danike Global Resources Ventures, No. 71 Textile Mill Road, Benin City. | 2016 | 6 Months after award | 29957705.26 | 75% | 7489426.31 | 22468278.95 | Ughelli North | On-going
110 | 389 | Construction of 2 No. 6 classroom block with toilets and offices at Ugbavweni Grammar School, Usiefrun, Ughelli South LGA | 8929224198 | Richland Continental Company, No. 42 Cemetery Road, Warri | 2016 | 6 Months after award | 70000000 | 100% | 46822626.46 | 23177373.54 | Ughelli South | Completed
111 | 392 | Construction of Modernized 2 No. 3 classroom block at Ugbavweni Grammar School, Usiefrun, Ughelli South LGA | 8929224198 | Richland Continental Company, No. 42 Cemetery Road, Warri | 2016 | 6 Months after award | 37635267.58 | 100% | 32845128.15 | 4790139.43 | Ughelli South | Completed
112 | 392 | Supply of Students Desks and Teachers Tables and Chairs to Ugbavweni Grammar School, Usiefrun, Ughelli South LGA | 8929224198 | Richland Continental Company, No. 42 Cemetery Road, Warri | 2016 | 6 Months after award | 2000000 | 100% | 0 | 2000000 | Ughelli South | Completed
113 | 309 | Construction of Administrative Block at Ezieh Primary School, Ezionum, Ukwuani LGA | 8929224198 | Atuwagate Enterprise, No.559A Zone 4 Phase 3 Gwagwalada Abuja. | 2016 | 6 Months after award | 11909627.56 | 100% | 10693193.07 | 1216434.49 | Ukwuani | Completed
114 | 309 | Construction of 3 Classroom Block with offices and Toilets at Ezieh Primary School, Ezionum, Ukwuani LGA | 8929224198 | Atuwagate Enterprise, No.559A Zone 4 Phase 3 Gwagwalada Abuja. | 2016 | 6 Months after award | 16579717.39 | 100% | 15750731.52 | 828985.87 | Ukwuani | Completed
115 | 309 | Renovation of 6 Classroom Block with offices Cubicles at Ezieh Primary School, Ezionum, Ukwuani LGA | 8929224198 | Atuwagate Enterprise, No.559A Zone 4 Phase 3 Gwagwalada Abuja. | 2016 | 6 Months after award | 13534095.07 | 100% | 11865876.02 | 1668219.05 | Ukwuani | Completed
116 | 309 | Supply of 125 Pupils Chairs/Desks and 15 Teachers Tables/Chairs to Ezieh Primary School, Ezionum, Ukwuani LGA | 8929224198 | Ojone Global & Sons Enterprises, Iwegbu and Sons Estate, Ogwashi-Uku. | 2016 | 6 Months after award | 4326205 | 100% | 4326205 | 0 | Ukwuani | Completed
117 | 450 | Construction of 1No.3 classroom block at Otolom Primary School, Ezionum, Ukwuani LGA | 8929224198 | Afam Anyasi and Sons,No. Ijaw Street, Warri. | 2016 | 6 Months after award | 18817633.79 | 25% | 4704408.45 | 14113225.34 | Ukwuani | On-going
118 | 450 | Supply of 1,443 Students and 121 Teachers furniture to Selected Schools, Ukwuani LGA | 8929224198 | Charleson Industrial Supplies Limited, No. 31 Obosi Street, Onitsha. | 2016 | 6 Months after award | 62364732.42 | 75% | 46773549.31 | 15591183.11 | Ukwuani | On-going
119 | 450 | Construction of 1No.3 classroom block with toilets and offices to Umutu Mixed Sec. School, Umutu, Ukwuani LGA | 8929224198 | Afam Anyasi and Sons,No. Ijaw Street, Warri. | 2016 | 6 Months after award | 18817633.79 | 100% | 3528306.34 | 15289327.45 | Ukwuani | Completed
120 | 393 | Construction of 1 No. 6 classroom block with toilets and offices at Ijakpa Primary School, Effurun, Uvwie LGA | 8929224198 | Danike Global Resources Ventures, No. 71 Textile Mill Road, Benin City. | 2016 | 6 Months after award | 35021147.37 | 20% | 8755286.84 | 26265860.53 | Uvwie | On-going
121 | 393 | Supply of Students Desks and Teachers Tables and Chairs to Selected Schools, Uvwie LGA | 8929224198 | Danike Global Resources Ventures, No. 71 Textile Mill Road, Benin City. | 2016 | 6 Months after award | 64000000 | 0% | 0 | 64000000 | Uvwie | On-going
122 | 394 | Supply of 2,315 Students and 386 Teachers furniture to Selected Schools, Warri North LGA | 8929224198 | Danike Global Resources Ventures, No. 71 Textile Mill Road, Benin City. | 2016 | 6 Months after award | 110000000 | 50% | 27734439.47 | 82265560.53 | Warri North | On-going
123 | 374 | Supply of Students Desks and Teachers Tables and Chairs to Selected Schools, Warri South I | 8929224198 | Ededeku Global Services Limited, No.12 Orogun Abbi Road Orogun. | 2016 | 6 Months after award | 100000000 | 100% | 100000000 | 0 | Warri South | Completed
124 | 395 | Supply of Students Desks and Teachers Tables and Chairs to Selected Schools, Warri South II | 8929224198 | Legend Global Concerns and Resources Ltd, No.3 Nnebisi Road, Asaba. | 2016 | 6 Months after award | 100000000 | 100% | 75007500 | 24992500 | Warri South | Completed
125 | 449 | Supply of 2,058 Students and 386 Teachers furniture to Selected Secondary Schools, Warri South West LGA | 8929224198 | Danike Global Resources Ventures, No. 71 Textile Mill Road, Benin City. | 2016 | 6 Months after award | 100000000 | 60% | 25000000 | 75000000 | Warri South West | On-going
126 | 453 | Construction of Administrative Block at Isaba Secondary School, Isaba, Warri South West LGA | 8929224198 | Jah-Obili Ventures, Km 30 Asaba-Benin Express Way, Asaba. | 2016 | 6 Months after award | 16444094.21 | 0% | 0 | 16444094.21 | Warri South West | On-going
127 | 453 | Construction of Science Laboratory Block at Isaba Secondary School, Isaba, Warri South West LGA | 8929224198 | Jah-Obili Ventures, Km 30 Asaba-Benin Express Way, Asaba. | 2016 | 6 Months after award | 21079530.74 | 0% | 0 | 21079530.74 | Warri South West | On-going
128 | 449 | Supply of 1,300 Students’ Furniture and 152 Teachers Furniture to Selected Schools, Warri South West LGA | 8929224198 | Jah-Obili Ventures, Km 30 Asaba-Benin Express Way, Asaba. | 2016 | 6 Months after award | 58397000 | 100% | 58397000 | 0 | Warri South West | Completed
129 | 20(i) | Refurbishing/Repair of Technical Equipment in the Six Technical Colleges, Across the State | 8929224198 | Peacealex Enterprises, 32, Summit Road, Asaba | 2016 | 6 Months after award | 10800000 | 100% | 10800000 | 0 | Across the State | Completed
130 | 5 | Supply of 1,136 Students’ Desks and 480 Teachers’ Furniture to Selected Schools /Redistribution across the State. | 8929224198 | Chioino Global Ventures, No.77 Imudia Street, Agbor. | 2016 | 6 Months after award | 50078062 | 100% | 50078062 | 0 | Across the State | Completed
TOTAL | [6 empty] | 4565543580.078 |  | 3546293868.07 | 1019249712.01

## 2017
DELTA STATE PPC FORM: ANNUAL PROCUREMENT PLAN FOR PROCURING ORGANIZATIONS NAME OF PROCURING ORGANISATION: MINISTRY OF BASIC AND SECONDARY EDUCATION
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
S/N | SUB-HEAD | PROJECT DESCRIPTION | APPROVED 2017 BUDGET (CAPITAL) | NAME OF CONTRACTOR | YEAR OF AWARD | EXPECTED DATE OF COMPLETION | CONTRACT SUM | % OF JOB COMPLETION | AMOUNT PAID TO DATE | OUTSTANDING PAYMENT | LGA | PROJECT STATUS
1 | 517180031 | Construction of 1No. Six Classroom Block each at Dei Primary School, Idumu-Ogo and Idumuje-Ugboko Primary School, Idumuje-Ugboko, Construction of 1No. 3 Classroom Block with offices and Toilets at Nkwor 1 Primary School, Idumuje-Unor and Supply of 18 Students’ and 7 Teachers’ Furniture, Aniocha North LGA | 13390700000 | Joti Joe Tessmarc Enterprise Phase IV Behind Legislative Quarters Okpanam Road, Asaba | 2017 | 6 Months after award | 99500000 | 100% | 99500000 | 0 | Aniocha North | Completed
2 | 509 | Renovation/Rehabilitation of 1No. Four (4) Classroom Block with stores, Offices, Toilets, 1No. Five (5) Classroom Block, 1No. three (3) Classroom Block with Stores and Supply of 140 Students’ and 25 Teachers’ Furniture, Odiani Mixed Secondary School, Uku-Nzu, Aniocha North LGA | 13390700000 | Carson Development Limited, 1, Ezena Street, Off Ugbor Road, Benin-City | 2017 | 6 Months after award | 49000000 | 100% | 6753550 | 42246450 | Aniocha North | Completed
3 | 516 | Renovation/Rehabilitation of 1no. 6 classroom block with stores and toilets, Laboratory block and Supply of 100 students’ desk and 20 Teachers’ furniture, Onicha-Ugbo Grammar School, Onicha-Ugbo, Aniocha North LGA | 13390700000 | Blue Pearls Global Links Ltd., Asaba | 2017 | 6 Months after award | 39000000 | 100% | 30000000 | 9000000 | Aniocha North | Completed
4 | 517 | Renovation/Rehabilitation of 1No. Six (6) Classroom block and Four (4) Classroom Block with an Examination Hall, Ewulu S/S, Ewulu, Aniocha South LGA | 13390700000 | Chudigwe Global Ventures 1, Pascal Adigwe Lane, Off DBS Road, Asaba | 2017 | 6 Months after award | 40000000 | 100% | 37999999.96 | 2000000.04 | Aniocha North | Completed
5 | 503 | Renovation/Rehabilitation of 1No. six (6) Classroom Block with stores, three Classroom Block, Completion of three Classroom block and Supply of 144 Students’ and Teachers’ Furniture, Ejeme Secondary school, Ejeme-Aniogor, Aniocha South LGA | 13390700000 | Theco Ventures, 224 Nnebisi Road, Asaba | 2017 | 6 Months after award | 49000000 | 100% | 49000000 | 0 | Aniocha South | Completed
6 | 517180031 | Construction of Six (6) Classroom Block with stores and Toilet facilities each at Etti-tti Amaka Primary School, Ubulu-Unor and Nsukwa Grammar School, Nsukwa. Construction of Three (3) classroom block with offices and toilets at Nwaeze Primary School, Ogwashi-Uku and supply of 40 Students’ and 10 Teachers’ Furniture, Aniocha South LGA | 13390700000 | Carson Development Ltd No. 1 Ezena Str., Off Ugbor Rd, Benin-City | 2017 | 6 Months after award | 98000000 | 60% | 24500000 | 73500000 | Aniocha South | On-going
7 | 517180031 | Construction of 1No. Six (6) Classroom Block with offices and toilets, Renovation of 1No. Six (6) classroom block, 1No. three (3) classroom Block and Supply of 600 Students’ and 44 Teachers’ Furniture at Ekade Primary School, Esanma, Bomadi LGA | 13390700000 | Sharpstone Company Limited, 199 Warri/Sapele Road, Warri | 2017 | 6 Months after award | 109948623.88 | 100% | 45638804 | 64309819.88 | Bomadi | Completed
8 | 529 | Renovation of Six (6) Classroom Block without stores and Supply of 250 students’ and 140 teachers’ furniture at Akugbene Grammar School, Akugbene, Bomadi LGA | 13390700000 | P.A Finchley Enterprises, No.54, Razaq Balogun Street, Surulere, Lagos. | 2017 | 6 Months after award | 39000000 | 60% | 9750000 | 29250000 | Bomadi | On-going
9 | 506 | Construction of Corpers’ lodge at Ogbein-Aima Secondary School, Bomadi LGA | 13390700000 | Keme-Ekea International, OgbeinAima, Bomadi | 2017 | 6 Months after award | 49000000 | 85% | 12000000 | 37000000 | Bomadi | On-going
10 | 517180031 | Renovation of Six Classroom Block with stores, Toilet Block at Temezubo Primary School, Okpokuno, Six Classroom Block with Headmasters’ office and Toilet at Ogbo Primary School, Okpokuno and Six Classroom Block expanded to include Toilet at Farade Primary School, Burutu LGA | 13390700000 | Ogbein Ventures, 3, Donowari Quarters, Okpokuno, Burutu LGA | 2017 | 6 Months after award | 99396154.62 | 100% | 92846306.96 | 6549847.66 | Burutu | Completed
11 | 505 | Renovation of Six (6) Classroom Block with office and Supply of Laboratory Equipment and 15 Teachers’ and 145 Students’ Furniture, Egodor Secondary School, Egodor, Burutu LGA | 13390700000 | B & D construction Enterprises, 2, Asupa Street, Edjeba, Warri | 2017 | 6 Months after award | 49786989.38 | 100% | 48169509.67 | 1617479.71 | Burutu | Completed
12 | 534 | Renovation of Six (6) Classroom Block, Administrative Block and Supply of 8 Teachers’ and 22 Students’ Furniture at Sokebolou Secondary School, Burutu LGA | 13390700000 | Thixo Affairs Enterprises, 8, Otuogwu Street, Asaba | 2017 | 6 Months after award | 39404997.64 | 100% | 9851249.41 | 29553748.23 | Burutu | Completed
13 | 531 | Refurbishment of 4 classroom block with cubicle and supply of 31 students’ and 10 teachers’ furniture at Gbesa Memorial Grammar School, Ojobo, Burutu LGA | 13390700000 | Borosugha Ventures, 13D, Lokoja Street, DSC, Ovwian Aladja | 2017 | 6 Months after award | 39785759.15 | 100% | 35861151.36 | 3924607.79 | Burutu | Completed
14 | 326 | Construction of Six (6) Classroom Block with office and Toilets and supply of 25 Students’ and 7 Teachers’ Furniture at Mein Grammar School, Kiagbodo, Burutu LGA | 13390700000 | P. A. Finchley Enterprises, No. 54, Razaq Balogun Street, Off Adeniran Ogunsanya, Surulere, Lagos | 2017 | 6 Months after award | 39000000 | 60% | 18182970.77 | 20817029.23 | Burutu | On-going
15 | 517180030 | Renovation of Gate House, Renovation and Reconstruction of failed portion of Fence, Completion of 1 bedroom Semi-detached Bungalow, renovation and conversion of existing Building to 4No. Bedsitter (Staff Quarters), renovation of abandoned 2 classroom block, 2 classroom block with office, 2No. Two (2) Classroom blocks, completion of three classroom block, construction of Male and Female Toilets (10 rooms), construction of 2,000 Gallon Capacity Electricity Powered Water Supply Scheme and Erection of State Govt. Branding Uniform Sign Post at Ogini Primary School, Obotebe, Burutu LGA | 13390700000 | Hug Engineering Services, Plot 38, 19th Street, DDPA, Effurun | 2017 | 6 Months after award | 96677297.64 | 100% | 24169324.41 | 72507973.23 | Burutu | Completed
16 | 504 | Additional works for the Construction, Furnishing and Equipping at Model Primary School, Burutu LGA | 13390700000 | Arkat Engineering Services Limited No. 2 Maro Street, By white House, Off Jakpa Road, Effurun | 2017 | 6 Months after award | 60754312.5 | 100% | 60754312.5 | 0 | Burutu | Completed
17 | 543 | Renovation of 1No. Nine Classroom Block, 1No. Three Classroom Block, Principals’ Quarters, Erection of Standard school sign Post (with the name of the school and new State Logo) and Erection of Standard and Uniform Signboard for State Government Projects at Umiaghwa Secondary School Oria-Abraka, Ethiope East LGA | 13390700000 | De-Mustard Seed System Services, No.6, Abiamuwe Street, Umunede | 2017 | 6 Months after award | 56764386.71 | 100% | 43324541.7 | 13439845.01 | Ethiope East | Completed
18 | 517180013 | i. Renovation of 1No. Six Classroom Block with Offices and Toilets, 1No. Three Classroom Science Laboratory Block with 4No. Stores, 1No. three Classroom Block with offices, 1 No. 3 classroom block, a Block of 10No. Toilet units and provision of 265 Students’ and 20 Teachers’ Furniture at Erho Secondary School ii. Renovation of 1No. Six Classroom Block without offices and Toilets at Abraka Grammar School, Abraka, Ethiope East LGA | 13390700000 | Peabody Terrace Enterprises House 1-38, Road 20, Victoria Garden City, Ajah, Lagos | 2017 | 6 Months after award | 98000000 | 100% | 24956766 | 73043234 | Ethiope East | Completed
19 | 517180036 | Renovation of 1No. Six (6) Classroom Block, 1No. Four (4) Classroom Block with offices, 1No. three (3) Classroom Block, Construction of access road and walkways with concrete interlocking paving stones with side kerbs, car parks, landscaping and renovation of front fence, Supply of 100 students’ furniture and Erection of school sign post with new Delta State Government Logo at Ejaife Primary School, Okpara-Inland, Ethiope East LGA | 13390700000 | Oruese International Nigeria Enterprises, Plot 27/28 DDPA Housing Estate, Ikoyo Avenue, Sapele | 2017 | 6 Months after award | 79724765.87 | 100% | 65100241.32 | 14624524.55 | Ethiope East | Completed
20 | 528 | Renovation of 1No. Seven (7) Classroom Block with offices and Supply of 310 pupils’ and 30 Teachers Furniture at Ejaife Primary School, Okpara-Inland, Ethiope East LGA | 13390700000 | Ebohgas Technical Enterprises, 17 PTI Road, Effurun | 2017 | 6 Months after award | 39402241.16 | 100% | 33659129.43 | 5743111.73 | Ethiope East | Completed
21 | 491 | Construction of Block wall Fence with Gate and Gate House and Supply of 130 students’ Desk and 19 Teachers’ furniture at Erhekevwe Secondary School, Jesse, Ethiope West LGA | 13390700000 | Momodiva Enterprises, No. 37 Anwai Road, Asaba | 2017 | 6 Months after award | 49000000 | 90% | 8171858.42 | 40828141.58 | Ethiope West | On-going
22 | 488 | Renovation of 1 No. Six Classroom block and 1 No. Five Classroom block at Okome Primary School, Ejemuonyawbe-Oghara, Ethiope West LGA | 13390700000 | Rizim Resources, No. 2, Iloba Ogbotobo Crescent, Off Nnebisi Road, Asaba | 2017 | 6 Months after award | 36242401.7 | 100% | 34396775.06 | 1845626.64 | Ethiope West | Completed
23 | 488 | Renovation of 1 No. six classroom block and erection of school sign post with new Delta State logo at Uherevie Primary School, Oghara at Uherevie Primary School, Oghara, Ethiope West LGA | 13390700000 | Elijah Delambeth Enterprises, Block D, Suite 2, No.1 Okpe Road, Sapele | 2017 | 6 Months after award | 18230743.14 | 100% | 18230743.14 | 0 | Ethiope West | Completed
24 | 488 | Reconstruction of 1 No. 6 Classroom Block with Toilets and stores, provision of 100 pupils desks and 10 teachers furniture, erection of school sign post with Delta State logo and provision of 50 pupils desks and 22 teachers furniture at Okome and Uherevie Primary Schools, Oghara, Ethiope West LGA | 13390700000 | Damari Global Enterprises, No. 48, DDPA Estate, Asaba | 2017 | 6 Months after award | 45440937.04 | 100% | 45440937.04 | 0 | Ethiope West | Completed
25 | 522 | Construction of 1No. Six (6) Classroom Block with Toilets and stores and Supply of 43 Students’ Furniture at Oghareki Secondary School, Oghareki, Ethiope West LGA | 13390700000 | Ethiope Treasures, 147, Aja Road, Oghareki, Oghara | 2017 | 6 Months after award | 39000000 | 100% | 39000000 | 0 | Ethiope West | Completed
26 | 517180031 | Construction of 2No. Six Classroom Block at Ugbenu Secondary School, Ugbenu and Supply of 425 Students’ and 30 Teachers’ Furniture at Ugbenu Secondary School, Ugbenu and Selected public schools, Ethiope West LGA | 13390700000 | Temiko Global Resources 7, Belefia Crescent, off Esiri Ugibeyiyi | 2017 | 6 Months after award | 96824894 | 80% | 96824894 | 0 | Ethiope West | On-going
27 | 517180015 | Renovation of 3No.3 Classroom Blocks without offices at Ngala Primary School, Boji-Boji Owa, Ika North East LGA | 13390700000 | Uditer Kiano Link 36A Core Area, Phase II GRA, Asaba | 2017 | 6 Months after award | 56242034.43 | 100% | 56242034.43 | 0 | Ika North East | Completed
28 | 517180015 | Renovation of 1No.8 Classroom Block With Attached Offices at Ngala Primary School, Boji-Boji Owa, Ika North East LGA | 13390700000 | Uditer Kiano Link 36A Core Area, Phase II GRA, Asaba | 2017 | 6 Months after award | 41678601.23 | 100% | 23902396.47 | 17776204.76 | Ika North East | Completed
29 | 517180015 | Renovation of 1No.7 Classroom Block with 4No. attached offices at Ngala Primary School, Boji-Boji Owa, Ika North East LGA | 13390700000 | Uditer Kiano Link 36A Core Area, Phase II GRA, Asaba | 2017 | 6 Months after award | 39335610.44 | 100% | 3868642.71 | 35466967.73 | Ika North East | Completed
30 | 517180015 | Renovation of 1No.6 Classroom Block with 6No. Attached offices at Ngala Primary School, Boji-Boji Owa, Ika North East LGA | 13390700000 | Glonneka Company, No.14 Esigie Street, Benin City | 2017 | 6 Months after award | 37176266.64 | 100% | 0 | 37176266.64 | Ika North East | Completed
31 | 517180015 | Reconstruction of Collapsed Sections, Completion and Rehabilitation of Perimeter Fence and Construction of 2No. Entrance and Metal Gate at Ngala Primary School, Boji-Boji Owa, Ika North East LGA | 13390700000 | Glonneka Company, No.14 Esigie Street, Benin City | 2017 | 6 Months after award | 33447475.33 | 100% | 21228680.73 | 12218794.6 | Ika North East | Completed
32 | 517180015 | Supply of 111 Students Desks and 45 Teachers Table and Chairs at Ngala Primary School, Boji-Boji Owa, Ika North East LGA | 13390700000 | J.K.M. Ventures, No. | 2017 | 6 Months after award | 6354480.02 | 100% | 6354480.02 | 0 | Ika North East | Completed
33 | 517180015 | Construction of 1No. Students/Teachers Toilet, Proposed Construction of 2No. Gate Houses, Electricity Connection to BEDC mains and Construction of Water Borehole, Ngala Primary School, Boji-Boji Owa, Ika North East LGA | 13390700000 | J.K.M. Ventures, No. | 2017 | 6 Months after award | 29473446.02 | 100% | 0 | 29473446.02 | Ika North East | Completed
34 | 517180015 | Renovation of 1 No. four (4) classroom block without offices and toilets, Ngala Primary School, Boji-Boji Owa, Ika North East LGA | 13390700000 | Okomof International, No.1 Lordsvine Close, off DLA Road, Asaba | 2017 | 6 Months after award | 13331250.83 | 100% |  | 13331250.83 | Ika North East | Completed
35 | 32 | Construction of Perimeter Fence and Gate House, Command Secondary School, Mbiri, Ika North East LGA | 13390700000 | Eric Kings Ventures No. 21 Omi Str., Owa-Alero | 2017 | 6 Months after award | 65221691.2 | 100% | 61830293.79 | 3391397.41 | Ika North East | Completed
36 | 525 | Renovation of 1No six Classroom Block with attached 6 No. offices and Toilets, Science Laboratory Block and Supply of 200 Student’s and 45 Teachers’ Furniture at Ute-Okpu Grammar School, Ute-Okpu, Ika North East LGA | 13390700000 | The Ecclessias Ventures Plot Ekete W/S Road, Orhuwhorun Road, Ekete | 2017 | 6 Months after award | 39186243.03 | 100% | 39186243.03 | 0 | Ika North East | Completed
37 | 512 | Revised award of contract on the Renovation of 1No six Classroom Block with cubicles,1No. 3 Classroom Block and Examination Hall and Supply of 410 Students and 67 Teachers Furniture at Owanta Mixed Secondary School, Owanta, Ika North East LGA | 13390700000 | Eric Kings Ventures, No. 21 Omi street, Owa-Alero | 2017 | 6 Months after award | 49672855.07 | 100% | 0 | 49672855.07 | Ika North East | Completed
38 | 517180031 | Renovation of T-Shaped Examination Hall with attached staff quarters, 1No. Four (4) Classroom/Laboratory Block with offices and Toilets, 1No. Six (6) Classroom Block with attached 2No. offices and Toilets, 1No. Six (6) classroom block with attached 6No. offices and Toilets and Supply of 230 Students’ and 49 Teachers’ Furniture at Ede Grammar School, Umunede, Ika North East LGA | 13390700000 | Kenlly Ugbebor Ventures, 42, Owanta Street, Boji-Boji, Agbor | 2017 | 6 Months after award | 99200000 | 75% | 99200000 | 0 | Ika North East | On-going
39 | 227 | Renovation of Science Laboratory Block, Renovation of 1No. 4 Classroom Block, Supply of 150 Student’s Desks and 20 Teacher’s Tables and Chairs and Supply of Science Equipment at Owerre-Olubor Mixed Secondary School, Owerre-Olubor, Ika North East LGA | 13390700000 | C-Hope Partnership 126, Old Lagos-Asaba Road, Agbor | 2017 | 6 Months after award | 52940000 | 100% | 36845673.11 | 16094326.89 | Ika North East | Completed
40 | 540 | Renovation of Six (6) Classroom Block with attached 6no. offices and construction of attached toilets, sagged roof and water logged six (6) classroom with attached office and 1no. boys’ Quarters to principals’ quarter at Owa-Alero Secondary School, Owa-Alero, Ika North East LGA | 13390700000 | Sumi Enterprises, Plot 6, WAEC Road, Core Area, Oshimili South, Asaba | 2017 | 6 Months after award | 46357991.18 | 100% | 11589497.8 | 34768493.38 | Ika North East | Completed
41 | 540 | Renovation of 2No. Six (6) Classroom Block with attached 6No. Offices and Toilets, Laboratory and Library Block with 3No. Offices and Toilets, 2No. Principal’s Quarters (3 Bedroom Flat) and Administrative Block at Owa-Alero Secondary School, Owa-Alero, Ika North East LGA | 13390700000 | EmmyBless Const. Ltd. No. 453 Nnebisi Road, Asaba | 2017 | 6 Months after award | 69792589.65 | 0% | 0 | 69792589.65 | Ika North East | On-going
42 | 227 | Renovation of 2No. Five (5) Classroom Block with 4 No. attached offices and Supply of 100 Students Desks and 15 Teachers’ Furniture at Owa-Oyibu Secondary School, Owa-Oyibu, Ika North East LGA | 13390700000 | Vovi International Company No. 14 Uwa Avenue, Off Adesua College Rd, Benin City | 2017 | 6 Months after award | 39700000 | 100% | 33873830.29 | 5826169.71 | Ika North East | Completed
43 | 49 | Renovation of 1No. Six (6) Classroom Block with 4No. attached cubicles and 2No. Administrative offices, Completion /Renovation of Perimeter Block wall fence, Construction of Gate and Gate House, Renovation of 1No. three Classroom Block with attached stores (Block A), Renovation of 1no. three Classroom Block with attached stores (Block B), Reconstruction of collapse 1No. three (3) Classroom Block with attached offices, Renovation of 1No. two (2) Classroom Block with attached offices, Supply of 200 Students’ desks and 50 Teachers’ furniture and Erection of School signboard with new State Government Logo at Iroro Primary School, Owa-Alero, Ika North East LGA | 13390700000 | Sumi Enterprises, Plot 6, Block 2 Core Area, Asaba | 2017 | 6 Months after award | 84743775.01 | 100% | 80769823.8 | 3973951.21 | Ika North East | Completed
44 | 517180026 | Renovation of 1No. Seven (7) Classroom Block with attached Science Laboratory and 1No. Six (6) Classroom Block with attached 6No. Offices at Abavo Mixed Secondary School, Abavo, Ika South LGA | 13390700000 | Pet-Uzor Nig. Enterprises No. 199 Warri/Sapele Rd, Warri | 2017 | 6 Months after award | 39426960.51 | 100% | 3630455.81 | 35796504.7 | Ika South | Completed
45 | 519 | Renovation of 1No. six (6) Classroom Block with attached 8 No. offices, Laboratory Block with offices and Supply of 210 Students’ and 34 Teachers’ Furniture at Abavo Mixed Secondary School, Abavo, Ika South LGA | 13390700000 | Nitram Resources, 1, Solomon Ovunwo Close, Rumuagholu, Portharcourt | 2017 | 6 Months after award | 39974065.14 | 100% | 37210955.73 | 2763109.41 | Ika South | Completed
46 | 517180031 | Renovation of 1 No. six (6) classroom block with attached 2 No. offices and six (6) No. cubicles each at Osaigbobu Primary School, Abavo and Alibudo Primary School, Ozanogogo, 1 No. 4 classroom block with attached offices and cubicles, 1 No. four (4) classroom block with 4 No. attached cubicles at Eno Primary School, Ozanogogo and supply of 403 students’ and 80 teachers’ furniture to various schools in Ika South LGA | 13390700000 | Danike Global Resources Ventures, 50, Josephine Nwaka Street, Okpanam Road, Asaba | 2017 | 6 Months after award | 99400000 | 100% | 99400000 | 0 | Ika South | Completed
47 | 513 | Renovation and Construction of Three (3) Classroom Block, Renovation of Five (5) Classroom Block, Construction Of Students’/Teachers’ Toilet and Renovation of Three (3) Classroom Block with Offices, Three (3) Classroom Block without Offices at Umu Primary School, Agbor-Alidinma and Anaza Primary School, Obi-Agbor, Ika South LGA | 13390700000 | Danike Global Resources Ventures, 50, Josephine Nwaka Street, Okpanam Road, Asaba | 2017 | 6 Months after award | 49700000 | 100% | 12425000 | 37275000 | Ika South | Completed
48 | 535 | Rehabilitation of 1No. Six Classroom Block with offices and Toilets, Supply of 20 Teachers and 82 Students’ Furniture and Erection of School Sign Post with new Delta State Logo at Atebo Comprehensive High School, Ekuigbo-Iyede, Isoko North LGA | 13390700000 | Kenny O. and Company, 7, Allor Close, Off Ezenei Avenue, Asaba | 2017 | 6 Months after award | 39937918.99 | 100% | 25079865.95 | 14858053.04 | Isoko North | Completed
49 | 514 | Construction of Corpers' Lodge Atebo Comprehensive High School, Ekuigbo-Iyede, Isoko North LGA | 13390700000 | Uzefav Nigeria Enterprises, No.5, Ogbaide Close, Ugbolokposo, Effurun | 2017 | 6 Months after award | 48800000 | 100% | 12200000 | 36600000 | Isoko North | Completed
50 | 517180031 | Construction of 1No. Six (6) Classroom Block with stores and Toilet facilities, Examination Hall, Residence of 4 Bedroom flat Akiewhe Secondary School, Akiewhe-Owhe and Supply of 732 Student’s and 206 Teachers’ furniture to Selected schools, Isoko North LGA | 13390700000 | Danike Global Resources Venture No. 71, Textile Mill Road, Benin City | 2017 | 6 Months after award | 119700000 | 100% | 29925000 | 89775000 | Isoko North | Completed
51 | 517180011 | Construction of 1No. Six (6) Classroom block at Uruogbo Primary School, Owhelogbo, Isoko North LGA | 13390700000 | J-Hova World Enterprises, No. 8, Otuowu Road, Asaba | 2017 | 6 Months after award | 38135137.09 | 100% | 9533784.27 | 28601352.82 | Isoko North | Completed
52 | 517180011 | Proposed Construction of a Perimeter block wall fence with Gatehouse demarcating the two schools at Uruogbo Primary school and Owhelogbo Secondary School, Owhelogbo, Isoko North LGA | 13390700000 | Oruese International Nigeria Enterprises, Plot 27/28, DDPA Housing Estate, Ikoyo Avenue, Sapele | 2017 | 6 Months after award | 11475871.53 | 100% | 10902077.96 | 573793.57 | Isoko North | Completed
53 | 517180013 | Construction of 1No.6 Classroom Blocks with Stores and Toilets at Enhwe Comprehensive High School, Enhwe, Isoko South LGA | 13390700000 | Charleson Industrial Supplies Ltd, No. 31 Obosi St, Onitsha | 2017 | 6 Months after award | 35021147.37 | 100% | 33270090 | 1751057.37 | Isoko South | Completed
54 | 517180013 | Supply of 100 Students and 20 Teachers Furniture at Enhwe Comprehensive High School, Enhwe, Isoko South LGA | 13390700000 | Charleson Industrial Supplies Ltd, No. 31 Obosi St, Onitsha | 2017 | 6 Months after award | 4622400 | 100% | 4622400 | 0 | Isoko South | Completed
55 | 517180013 | Supply of 100 Students and 20 Teachers Furniture at Igbide Grammar School, Enhwe, Isoko South LGA | 13390700000 | Charleson Industrial Supplies Ltd, No. 31 Obosi St, Onitsha | 2017 | 6 Months after award | 4622400 | 100% | 4622400 | 0 | Isoko South | Completed
56 | 517180013 | Supply of 100 Students and 20 Teachers Furniture at Olomoro Comprehensive High School, Olomoro, Isoko South LGA | 13390700000 | Charleson Industrial Supplies Ltd, No. 31 Obosi St, Onitsha | 2017 | 6 Months after award | 4622400 | 100% | 4622400 | 0 | Isoko South | Completed
57 | 517180031 | Construction of 1No. Six (6) Classroom Block with stores and Toilets at Owholeme Primary School, Olomoro Construction of 1No. Six (6) Classroom Block with stores and Toilets at Eru Primary School, Igbide, Isoko Provision of 510 Students’ and 105 Teachers’ Furniture to Selected Schools in Isoko South LGA | 13390700000 | Beevets Nigeria, No. 16, Okumagba Avenue, Warri | 2017 | 6 Months after award | 99710810.23 | 60% | 48368238.55 | 51342571.68 | Isoko South | On-going
58 | 517180031 | Proposed construction of a prototype three (3) classroom block with offices and toilets (upland communities) and Erection of School Sign Post with New Delta State Govt. Logo at Eweri Primary School, Emede, Proposed construction of a prototype Six (6) classroom block with offices and toilets (upland communities) and Erection of School Sign Post with New Delta State Govt. Logo at College of Education Agbor, Irri Study Centre Renovation of 4 classroom Block without offices and Erection of School Sign Post with New Delta State Govt. Logo at Uzi Primary School, Oleh Supply of 481 Students’ and 60 teachers’ Furniture to Selected schools in Isoko South LGA | 13390700000 | Camarilo Ventures, 18, Rhodes Crescent, Apapa, Lagos | 2017 | 6 Months after award | 99966049.45 | 60% | 24999012.36 | 74967037.09 | Isoko South | On-going
59 | 500 | Construction of Perimeter Block wall Fence with Gate, Gate-House, Mini Toilet/ Generator space Building, Borehole with small Overhead water Tank/stand and supply of 18 Teachers’ and 280 Students’ Furniture at Evoja Primary School, Oleh | 13390700000 | Mirostoher Venture, 22, Summit Road, Asaba | 2017 | 6 Months after award | 49000000 | 100% | 46550000 | 2450000 | Isoko South | Completed
60 | 517180031 | i. Construction of Prototype Three (3) classroom Block with stores and Toilets at Umuoru Secondary School, Umuoru ii. Renovation of 3No. Three (3) classroom Blocks, 2No. Two (2) Classroom blocks, Construction of Prototype Three (3) Classroom Block with stores and toilets, Administrative Block at Ozoma-Ukwu Primary School, Ashaka iii. Supply of 960 Students’ and 180 teachers’ Furniture, Ndokwa East LGA | 13390700000 | Oruese International Nigeria Enterprises, Plot 27/28, DDPA Housing Estate, Ikoyo Avenue, Sapele | 2017 | 6 Months after award | 147143152.19 | 100% | 147143152.19 | 0 | Ndokwa East | Completed
61 | 494 | Renovation of 1 No. six classroom block, 1 no. 4 classroom block and construction of 1 no. 3 classroom block at Isselegu Primary School, Isselegu, Ndokwa East LGA | 13390700000 | Ochikap Nig. Enterprises, No.6, Dennis Iyamu Crescent, off Ibusa Road, Akwuofu, Asaba | 2017 | 6 Months after award | 48838355.53 | 100% | 12209588.88 | 36628766.65 | Ndokwa East | Completed
62 | 520 | Construction of Library Block and Renovation of 1No. Four (4) Classroom Block with stores and Toilets at Community S/S, Ogbole-Ogume, Ogume, Ndokwa West LGA | 13390700000 | Icab Global Enterprise, 3, Ogume/Kwale Road, Ogume | 2017 | 6 Months after award | 38317858 | 100% | 19579464.5 | 18738393.5 | Ndokwa West | Completed
63 | 497 | Construction of Perimeter Fencing, Renovation of Administrative Block and Supply of 40 Students’ and 5 Teachers’ Furniture at Emu-Obodeti commercial Secondary School, Emu-Obodeti, Ndokwa West LGA | 13390700000 | Ernest Sons & Daughters Ventures, No.29, Umusam Road, Kwale. | 2017 | 6 Months after award | 49376811 | 50% | 12344202.75 | 37032608.25 | Ndokwa West | On-going
64 | 517180031 | 1. Renovation of 1No. three Classroom Block with offices and 1No. 6 Classroom Block without offices at Ibabu Primary School, Ibabu, Onicha Ukwuani, 2. Renovation of 1No. Six classroom block with stores, 1No. three Classroom Block with two offices and an Administrative Block at Iyashili Primary School, Umusan, Kwale, 3. Renovation of 2No. three classroom blocks without offices (Blocks A & B), Renovation of Perimeter wall fence at Ulogwe Primary School, Ulogwe-Isumpe 4. Renovation of Eight Classroom Block with stores at Adege Primary School, Ndemili, Ndokwa West LGA | 13390700000 | R.E.A Nigeria Limited 3, Oghara Street, DDPA Estate, Off DBS Road, Asaba | 2017 | 6 Months after award | 98000000 | 50% | 59239480.33 | 38760519.67 | Ndokwa West | On-going
65 | 517180032 | Renovation of a Block of Four (4) Classrooms without stores at Nduku Primary School, Ogbole-Ogume, Ndokwa West LGA | 13390700000 | Transnal Integrated Services, No.195 Ikorodu Road, Palmgrove, Lagos | 2017 | 6 Months after award | 8407134.33 | 70% | 5872282 | 2534852.33 | Ndokwa West | On-going
66 | 517180032 | Renovation of a Block of Four (4) Classrooms with stores at Nduku Primary School, Ogbole-Ogume, Ndokwa West LGA | 13390700000 | Transnal Integrated Services, No.195 Ikorodu Road, Palmgrove, Lagos | 2017 | 6 Months after award | 9143567.54 | 100% | 8232925.69 | 910641.85 | Ndokwa West | Completed
67 | 517180032 | Renovation of Perimeter Fencing at Nduku Primary School, Ogbole-Ogume, Ndokwa West LGA | 13390700000 | Transnal Integrated Services, No.195 Ikorodu Road, Palmgrove, Lagos | 2017 | 6 Months after award | 5999647.2 | 100% | 5999647.2 | 0 | Ndokwa West | Completed
68 | 517180032 | Construction of Toilets at Nduku Primary School, Ogbole-Ogume, Ndokwa West LGA | 13390700000 | Transnal Integrated Services, No.195 Ikorodu Road, Palmgrove, Lagos | 2017 | 6 Months after award | 6635684.21 | 100% | 6635684.21 | 0 | Ndokwa West | Completed
69 | 517180032 | Construction of Portable Water Supply Scheme at Nduku Primary School, Ogbole-Ogume, Ndokwa West LGA | 13390700000 | Transnal Integrated Services, No.195 Ikorodu Road, Palmgrove, Lagos | 2017 | 6 Months after award | 13392705.27 | 100% | 12723070.01 | 669635.26 | Ndokwa West | Completed
70 | 517180032 | Supply of 20 Teachers and 200 Pupils Furniture at Nduku Primary School, Ogbole-Ogume, Ndokwa West LGA | 13390700000 | Transnal Integrated Services, No.195 Ikorodu Road, Palmgrove, Lagos | 2017 | 6 Months after award | 7866261.45 | 100% | 7866261.45 | 0 | Ndokwa West | Completed
71 | 517180013 | Construction of 1 No. Six (6) Classroom Block and Supply of Furniture at Ogbagu Mixed Secondary School, Ogbagu-Ogume, Ndokwa West LGA | 13390700000 | Agason Services Nigeria 39A Umusadege Road, Kwale | 2017 | 6 Months after award | 41388637.1 | 100% | 41388637.1 | 0 | Ndokwa West | Completed
72 | 532 | Construction of Administrative Block, Renovation of 1no. Three (3) Classroom Block, 1No. four (4) Classroom block and Construction of Teachers’ Toilet at Etua Primary School, Ogo-Etua, Ndokwa West LGA | 13390700000 | Giwa & Associates, 20, Ezenei Avenue, Asaba | 2017 | 6 Months after award | 39627519 | 60% | 9906879.75 | 29720639.25 | Ndokwa West | On-going
73 | 517180031 | Construction of Science Laboratory and Examination Hall at Osubi Secondary School, Construction of 1No. Prototype Six Classroom Block with stores and toilet facilities each at Evwereke Primary School, Osubi, Okirikperhe Primary School, Okirikperhe and Oviri-Okpe Secondary School, Oviri-Okpe respectively and supply of furniture, Okpe LGA | 13390700000 | Danike Global Resources Venture No. 71, Textile Mill Road, Benin City | 2017 | 6 Months after award | 195646814.67 | 80% | 99844433.7 | 95802380.97 | Okpe | On-going
74 | 487 | Construction of Perimeter Block wall fence of 1,004.07 meters with gate and gate house, Erection of Standard schools sign Post (with the name of the school and new State Logo) and Erection of Standard and Uniform Signboard for State Government Projects, Okpe LGA | 13390700000 | Omitelojor Ventures, No.22 Redeemers’ Street, off Mariam Babangida Road, Asaba. | 2017 | 6 Months after award | 59000000 | 90% | 14750000 | 44250000 | Okpe | On-going
75 | 533 | Renovation of Six (6) Classroom Block, Three (3) Classroom Block, Laboratory Block and Supply of 293 Students’ and 22 Teachers’ Furniture at Orhue Secondary school, Mereje, Okpe LGA | 13390700000 | Charlech Limited, 69, Airport Road, Opp. Delta Career College, Warri | 2017 | 6 Months after award | 39000000 | 70% | 36076992 | 2923008 | Okpe | On-going
76 | 507 | Renovation of Laboratory Block, Introductory Technology Block, Supply of Laboratory Equipment and Supply of 110 Students’ and 22 Teachers’ Furniture at Ugbokodo Secondary School, Ugbokodo, Okpe LGA | 13390700000 | Temiko Global Resources, 7, Belefia Crescent, Ugbeyiyi, Sapele | 2017 | 6 Months after award | 48842950.08 | 100% | 43991381.93 | 4851568.15 | Okpe | Completed
77 | 523 | Renovation of Six (6) Classroom Block, Six (6) Classroom Block, Principal’s Office and supply of 186 student’s Desks and 21 Teachers’ Furniture at Oha Secondary School, Oha, Okpe LGA | 13390700000 | Uticote Nigeria Company, Kilometer 3, Osubi Express Way, Osubi | 2017 | 6 Months after award | 39000000 | 100% | 28880992.2 | 10119007.8 | Okpe | Completed
78 | 517180030 | Demolition and Reconstruction of 2No.3 Classroom Blocks with 3No. Stores and 1No. Office at Akwukwu-Igbo Grammar School, Akwukwu-Igbo, Oshimili North LGA | 13390700000 | Rizim Resources, No.2 Iloba Ogbotobo Crescent, off Nnebisi Road, West End, Asaba | 2017 | 6 Months after award | 36483739.18 | 100% | 34204233.39 | 2279505.79 | Oshimili North | Completed
79 | 517180030 | Renovation of 3 Classroom Block with 2No. Offices at Akwukwu-Igbo Grammar School, Akwukwu-Igbo, Oshimili North LGA | 13390700000 | Rizim Resources, No.2 Iloba Ogbotobo Crescent, off Nnebisi Road, West End, Asaba | 2017 | 6 Months after award | 9550258.77 | 100% | 8854043.94 | 696214.83 | Oshimili North | Completed
80 | 517180030 | Renovation of Perimeter Fence and Construction of Gate House at Akwukwu-Igbo Grammar School, Akwukwu-Igbo, Oshimili North LGA | 13390700000 | Rawds and Steel Enterprise, No.19 Burutu Drive, off Infant Jesus Road, Asaba | 2017 | 6 Months after award | 7056766.15 | 100% | 7056766.15 | 0 | Oshimili North | Completed
81 | 517180030 | Supply of 150 Students Desks and 25 Teachers Tables at Akwukwu-Igbo Grammar School, Akwukwu-Igbo, Oshimili North LGA | 13390700000 | Rainbow Properties and Resort, No.24 Ibusa Road. Opp. ACCIMA Office Asaba | 2017 | 6 Months after award | 6814500.01 | 100% | 6814500.01 | 0 | Oshimili North | Completed
82 | 517180011 | Supply of 540 Students Desks and 100 Teachers Furniture at Oruchi Comprehensive Secondary School, Okpanam, Oshimili North LGA | 13390700000 | Dajoc Investment Limited, No. 22 Memeh St. Boji-Boji Agbor | 2017 | 6 Months after award | 26164800.06 | 100% | 26164800.06 | 0 | Oshimili North | Completed
83 | 517180011 | Provision of Students/Teachers Toilet at Oruchi Comprehensive Secondary School, Okpanam, Oshimili North LGA | 13390700000 | Dajoc Investment Limited, No. 22 Memeh St. Boji-Boji Agbor | 2017 | 6 Months after award | 5741305.21 | 100% | 5741305.21 | 0 | Oshimili North | Completed
84 | 517180011 | Construction of Science Laboratory at Oruchi Comprehensive Secondary School, Okpanam, Oshimili North LGA | 13390700000 | Norjyx and Partners, No. 4 Dada Ezechei Avenue By Vanguard Newspaper, Asaba | 2017 | 6 Months after award | 22468238.13 | 30% | 5617059.53 | 16851178.6 | Oshimili North | On-going
85 | 517180011 | Construction of Administrative Block and Supply of 30 Teachers furniture at Oruchi Comprehensive Secondary School, Okpanam, Oshimili North LGA | 13390700000 | Charleson Industrial Supplies Ltd, No. 31 Obosi St, Onitsha | 2017 | 6 Months after award | 26620651.25 | 100% | 26620651.25 | 0 | Oshimili North | Completed
86 | 517180011 | Construction of Borehole at Oruchi Comprehensive Secondary School, Okpanam, Oshimili North LGA | 13390700000 | Charleson Industrial Supplies Ltd, No. 31 Obosi St, Onitsha | 2017 | 6 Months after award | 1770299.91 | 100% | 1770299.91 | 0 | Oshimili North | Completed
87 | 517180030 | Provision of Students’/Teachers’ Toilet and Supply of 180 Students’ and 20 Teachers’ Furniture at Government Secondary School, Atuma-Iga, Oshimili North LGA | 13390700000 | Felix & Felix Nig. Const. No. 22, Infant Jesus Roard, Asaba | 2017 | 6 Months after award | 13603705.21 | 100% | 13603705.21 | 0 | Oshimili North | Completed
88 | 511 | Revised award of contract on the construction of reinforced concrete drainage/external works, 1No. Six Classroom Block, 1No. Three Classroom block with two Offices and repainting of Administrative block at Mgbala Primary School, Okpanam, Oshimili North LGA | 13390700000 | Rawds & Steel Enterprise, No. 19 Burutu drive, Off Infant Jesus Road, Asaba | 2017 | 6 Months after award | 48193619.6 | 100% | 48193619.6 | 0 | Oshimili North | Completed
89 | 517180030 | Construction of 1no. Six (6) Classroom Block at Government Secondary School, Atuma-Iga, Oshimili North LGA | 13390700000 | Rainbow Properties & Resort, 1st Floor Michelin Tyre Service Building, Ibusa Road, Asaba | 2017 | 6 Months after award | 35021147.37 | 100% | 33010804.39 | 2010342.98 | Oshimili North | Completed
90 | 517180031 | Construction of 2 No. 3 classroom blocks, 1 No. 6 classroom block (L-shaped) without toilets, renovation/rehabilitation of 3 classroom block with offices, construction of pupils’ toilets, teachers’ toilets, renovation of 4 No. 3 classroom blocks (A,B,C and D) at Akwue Primary School, Ogboli, Ibusa, Oshimili North LGA | 13390700000 | Tunjila Corporate Services 14 DBS Road, Asaba | 2017 | 6 Months after award | 108000000 | 80% | 27000000 | 81000000 | Oshimili North | On-going
91 | 517180011 | Renovation of a Block of three classroom with hall and Erection of State Government branding uniform project signboard at Madonna School for Children with special needs, Okpanam, Oshimili North LGA | 13390700000 | 7th June Cnsults L22, Centre Plaza, DLA Road, Asaba | 2017 | 6 Months after award | 14551716.78 | 100% | 13653130.94 | 898585.84 | Oshimili North | Completed
92 | 19(ii) | Furnishing of Agricultural Science/Physics Laboratory, Biology Laboratory and Chemistry Laboratory at Model Secondary School, GRA, Asaba, Oshimili South LGA | 13390700000 | Carson Development Limited, 1, Ezena Street, Off Ugbor Road, Benin-City | 2017 | 6 Months after award | 21847320 | 100% | 21847320 | 0 | Oshimili South | Completed
93 | 517180013 | Supply of 300 Students’ double Desks, 15 Teachers’ Furniture and Science Equipment at Model Secondary School, GRA, Asaba, Oshimili South LGA | 13390700000 | Thixo Affairs Enterprises, No. 8 Otuogwu Street, Asaba. | 2017 | 6 Months after award | 21700000 | 100% | 21700000 | 0 | Oshimili South | Completed
94 | 517180011 | Construction of 1No. three Classroom Block with 3No. stores and 1No. Office, Oko Mixed Secondary School, Oko, Oshimili South LGA | 13390700000 | Gostart Giant Enterprise 10B, Udoka Odogwu Street, Off Falcon Club Rd, DLA, Asaba | 2017 | 6 Months after award | 17321869.61 | 100% | 16455776.09 | 866093.52 | Oshimili South | Completed
95 | 515 | Renovation of 1 No. six classroom block with 6no. stores, 3 classroom block with 3no. stores and an office and construction Administrative block and staff room, Niger College, Asaba, Oshimili South LGA | 13390700000 | Julian Ventures, No.43, Airport Road, Benin-City | 2017 | 6 Months after award | 50000000 | 100% | 50000000 | 0 | Oshimili South | Completed
96 | 517180011 | Renovation of 1No. Seven (7) Classroom Block with 4No. Stores, 1No. 6 Classroom Block with 1No. Offices and Stores at Oko Mixed Secondary School, Oko, Oshimili South LGA | 13390700000 | Upstream well completion services 2, Echendu Street, off Circular Road, Woji, PH. | 2017 | 6 Months after award | 42747867.55 | 100% | 42747867.55 | 0 | Oshimili South | Completed
97 | 517180011 | Supply of 80 students’ desks and 15 teachers’ tables and chairs at Oko Mixed Secondary School, Oko, Oshimili South LGA | 13390700000 | Bramanda Limited, 18, Queen Mowa Drive, Asaba | 2017 | 6 Months after award | 3716900 | 100% | 3716900 | 0 | Oshimili South | Completed
98 | 517180011 | supply of 200 students’ and 15 teachers at Asaba College, Asaba (Isioma Onyeobi College), Oshimili South LGA | 13390700000 | Thixo Affairs Enterprises, No. 8, Otuowu Street, Asaba | 2017 | 6 Months after award | 11048050 | 100% | 11048050 | 0 | Oshimili South | Completed
99 | 517180011 | Renovation/Rehabilitation of 1no Six (6) Classroom Block with toilet and offices at Asaba College, Asaba (Isioma Onyeobi College), Oshimili South LGA | 13390700000 | Raine Global Concept, No.1, Okelue Street, Asaba | 2017 | 6 Months after award | 27398782.63 | 100% | 27398782.63 | 0 | Oshimili South | Completed
100 | 517180011 | Renovation/Rehabilitation of 1no five (5) Classroom Block with toilet and offices at Asaba College, Asaba (Isioma Onyeobi College), Oshimili South LGA | 13390700000 | Dada Global Resources, 1, Iyibu Lane, Umuezei, Asaba | 2017 | 6 Months after award | 25038666.25 | 100% | 23786732.93 | 1251933.32 | Oshimili South | Completed
101 | 517180011 | Renovation of 1No. Six (6) Classroom Block with 1No. Office and Store and Construction of 1No. Three (3) Classroom Block with 3No. Stores and 1No. Office at Oko Secondary School, Oshimili South LGA | 13390700000 | Wazinga Global Services, 6, Sir Chukwunwike Street, Off Asaba/Benin exp. Way | 2017 | 6 Months after award | 40000000 | 100% | 40000000 | 0 | Oshimili South | Completed
102 | 517180031 | Construction of 1No. Six (6) Classroom Block each at Zappa and West-End Mixed Secondary Schools, Asaba and Supply of 45 Teachers’ and 250 Students’ Double seater Furniture each, Oshimili South LGA | 13390700000 | Carson Development Ltd No. 1 Ezena Str., Off Ugbor Rd, Benin-City | 2017 | 6 Months after award | 98500000 | 80% | 73875000 | 24625000 | Oshimili South | On-going
103 | 517180013 | Rehabilitation of 1 No. 3 Classroom Block, 1 No. 3 Classroom Block with Headmasters’ Office and Supply of 100 Students’ Desks and 10 Teachers’ Tables and Chairs at Akedeinowei Primary School I Toru-Angiama, Patani | 13390700000 | Erhias Boris Ventures No. 3, Agada Street, Asaba | 2017 | 6 Months after award | 42752985.24 | 100% | 41329297.73 | 1423687.51 | Patani | Completed
104 | 517180013 | Rehabilitation of 1No. Six (6) Classroom Block at Akedeinowei Primary School I Toru-Angiama, Patani | 13390700000 | Chu-Emma Global Services 77,Imudia Street, Agbor | 2017 | 6 Months after award | 35108657.88 | 100% | 35108657.88 | 0 | Patani | Completed
105 | 517180031 | Renovation of 1No. Six (6) Classroom Block, 1No. Three (3) Classroom Block, Construction of Gate House at at Odorubu Primary School, Uduovie Renovation of 1No. Four (4) Classroom Block at Aven Primary School, Aven. Renovation of 1No. Four (4) Classroom Block at Ayinma Primary School, Abari Supply of 1027 Students’ and 350 Teachers’ Furniture in Patani LGA | 13390700000 | Danike Global Resources Ventures, 50, Josephine Nwaka Street, Okpanam Road, Asaba | 2017 | 6 Months after award | 99977522.2 | 20% | 24994380.55 | 74983141.65 | Patani | On-going
106 | 517180013 | Supply of 200 Students’ and 24 Teachers’ Furniture at Model Secondary School, Patani | 13390700000 | Chovis Multilinks 2, Ogbogu Onyeayan, Close, Off Okpanam Road, Asaba | 2017 | 6 Months after award | 9029800 | 100% | 9029800 | 0 | Patani | Completed
107 | 517180013 | Renovation of Principals’ Lodge, Vice Principals’ Lodge, Examination Hall, 1No. Six (6) Classroom Block with stores and Toilets at Model Secondary School, Patani | 13390700000 | Eregha Nigeria Limited, No.2, Esievo Lane, Effurun | 2017 | 6 Months after award | 74419883.91 | 85% | 33483618.79 | 40936265.12 | Patani | On-going
108 | 517180013 | Renovation of 3 No. 6 classroom block with stores and toilets at Model Secondary School, Patani | 13390700000 | Elp Integrated Services 1, Rahi Avenue, off Km 16 East/West Road, Ruomosi, Port Harcourt | 2017 | 6 Months after award | 76303003.8 | 85% | 19075751 | 57227252.8 | Patani | On-going
109 | 530 | Renovation of 2No. Four (4) Classroom block and Supply of 53 Students’ and 10 Teachers’ Furniture at Bolu-Angiama Secondary School, Bolu-Angiama, Patani | 13390700000 | Doubi & Amais Enterprises, No. 5 Bendid Drive, Asaba | 2017 | 6 Months after award | 38984603.68 | 100% | 38984603.68 | 0 | Patani | Completed
110 | 495 | Renovation of six (6) Classroom Block with stores (Block 1) and Supply of 423 Students’ and 25 Teachers’ Furniture at Agoloma Primary School, Agoloma, Patani | 13390700000 | S.P.I Nigeria Enterprises, 2, Ekise Quarters, Patani | 2017 | 6 Months after award | 49520784.77 | 100% | 45745048.2 | 3775736.57 | Patani | Completed
111 | 517180011 | Reconstruction of Hostel Block at Chude Girls’ Model Secondary School, Sapele | 13390700000 | Raphat Corporate Associates, No. 14 Uwa Avenue, Off Adesua College Rd, Benin City | 2017 | 6 Months after award | 74538930.36 | 100% | 63644079.88 | 10894850.48 | Sapele | Completed
112 | 517180011 | Reconstruction of part of collapse Fence and Gate House at Chude Girls’ Model Secondary School, Sapele | 13390700000 | Pat-Gone Enterprises Plot 10 Ijia Str., Ogba, Ikeja | 2017 | 6 Months after award | 24779483.05 | 100% | 0 | 24779483.05 | Sapele | Completed
113 | 517180011 | Renovation of Administrative Block at Chude Girls’ Model Secondary School, Sapele | 13390700000 | Pat-Gone Enterprises Plot 10 Ijia Str., Ogba, Ikeja | 2017 | 6 Months after award | 16740208.62 | 100% | 0 | 16740208.62 | Sapele | Completed
114 | 517180011 | Renovation of Principal’s Quarter II Building at Chude Girls’ Model Secondary School, Sapele | 13390700000 | JO-1 Ventures No. 2 Obiemashi Str., Asaba | 2017 | 6 Months after award | 8451209.91 | 100% | 8451209.91 | 0 | Sapele | Completed
115 | 517180011 | Renovation of Laboratory with Office Block at Chude Girls’ Model Secondary School, Sapele | 13390700000 | Rodit. E Nigeria Enterprises No. 4 Ajaokuta Str., DSC, Aladja, Warri | 2017 | 6 Months after award | 32365572.23 | 100% | 32365572.23 | 0 | Sapele | Completed
116 | 517180011 | Renovation of Examination Hall at Chude Girls’ Model Secondary School, Sapele | 13390700000 | Rodit. E Nigeria Enterprises No. 4 Ajaokuta Str., DSC, Aladja, Warri | 2017 | 6 Months after award | 26971642.34 | 100% | 26971642.34 | 0 | Sapele | Completed
117 | 517180011 | Renovation of Six (6) Classroom Block without offices at Chude Girls’ Model Secondary School, Sapele | 13390700000 | Five Hold Agency Enterprise No. 1 Samtam House, Okpanam Rd, Asaba | 2017 | 6 Months after award | 31486574.76 | 100% | 31486574.76 | 0 | Sapele | Completed
118 | 517180011 | Renovation of Dinning Hall and an attached Kitchen Block at Chude Girls’ Model Secondary School, Sapele | 13390700000 | Vetic Nig. Enterprises No. 12 Onyekosor Str., Off Marble Hill Sch., Okpanam | 2017 | 6 Months after award | 23014521.37 | 100% | 23014521.37 | 0 | Sapele | Completed
119 | 517180011 | Renovation of Kitchen Store Block and a Walkway and Construction of Solar powered water supply scheme at Chude Girls’ Model Secondary School, Sapele | 13390700000 | Eric Kings Ventures No.21 Omi Str., Owa-Alero | 2017 | 6 Months after award | 30361036.9 | 100% | 30361036.9 | 0 | Sapele | Completed
120 | 517180011 | Supply of 45 Teachers’ and 200 Students’ Furniture at Chude Girls’ Model Secondary School, Sapele | 13390700000 | Azani & Azani Ventures, 14, Joel Close, Off Marine Street, Agbor | 2017 | 6 Months after award | 9487800 | 100% | 9487800 | 0 | Sapele | Completed
121 | 517180011 | Renovation of Principals’ Quarters Building at Chude Girls’ Model Secondary School, Sapele | 13390700000 | Ve-Man Global Enterprise, 104, Okpanam Road, Asaba | 2017 | 6 Months after award | 23595214.65 | 100% | 0 | 23595214.65 | Sapele | Completed
122 | 517180031 | Renovation of 1 No. six (6) classroom block with offices and toilets at Egbele Primary School, Egbele-Elume and provision of 1,300 students’ and 162 teachers’ furniture in Sapele LGA. | 13390700000 | De Mustard Seed Services, No. 6, Abiamuwe Street, Umunede | 2017 | 6 Months after award | 77514055.06 | 70% | 41496300.76 | 36017754.3 | Sapele | On-going
123 | 517180031 | Renovation of laboratory Block, 1No. Six (6) Classroom Block and Supply of School Furniture at Elume Grammar School, Elume, Sapele LGA | 13390700000 | Desco Nigeria Enterprises, 71, DLA Road, Asaba | 2017 | 6 Months after award | 48973146.24 | 100% | 48973146.24 | 0 | Sapele | Completed
124 | 508 | Renovation of 1No. Seven (7) Classroom Block, 1No. Six (6) Classroom Block and supply of 166 Student’s and 25 Teacher’s furniture at Ekete Secondary School, Ekete, Udu LGA | 13390700000 | Besa Mercantile Company, No. 18 Inalu Street, Umuagu Qtrs, Asaba | 2017 | 6 Months after award | 74106602.89 | 100% | 74106602.89 | 0 | Udu | Completed
125 | 517180031 | i. Renovation of six (6) classroom block with offices at Ovwian Secondary School, Ovwian ii. Renovation of six (6) classroom block with offices at Owhrode Secondary School, Owhrode iii. Construction of 1No. six (6) classroom block with toilets and offices at Oghior Secondary School, Oghior iv. Provision of 280 Students’ furniture and 30 Teachers’ furniture, Udu LGA | 13390700000 | Kokobond International Concept Ltd., No.3, Otebor Hall, Orhuwhorun | 2017 | 6 Months after award | 99000000 | 100% | 41840696.41 | 57159303.59 | Udu | Completed
126 | 517180011 | Renovation of six classroom block with offices, Demolition and Reconstruction of Science Laboratory block and supply of 103 students’ and 10 teachers’ furniture at Otovwodo Grammar School, Otovwodo, Ughelli North LGA | 13390700000 | Westwood Ventures, No.15, Ogbeitive Quarters, Ughelli | 2017 | 6 Months after award | 47000000 | 100% | 47000000 | 0 | Ughelli North | Completed
127 | 517180031 | Renovation of 1No. Six (6) Classroom Block with offices, 1No. 6 Classroom Block with offices and Toilets, Uncompleted Dilapidated three classroom Block with attached staff room, Renovation of laboratory Building (demonstration units), 1No. three Classroom block with offices, Modernized six (6) Classroom Block and Provision of 100 students’ and 22 Teachers’ Furniture at Eni Grammar School, Evwreni, Ughelli North LGA | 13390700000 | Erhias Boris Ventures No. 3, Agada Street, Asaba | 2017 | 6 Months after award | 98000000 | 100% | 98000000 | 0 | Ughelli North | Completed
128 | 254 | Supply of 450 students’ and 30 Teachers’ Furniture and Supply of Science Equipment at Uwheru Grammar School, Uwheru, Ughelli North LGA | 13390700000 | Innapo Ventures No. 17, Gbenga Street, Agbor | 2017 | 6 Months after award | 27322434 | 65% | 0 | 27322434 | Ughelli North | On-going
129 | 517180031 | Construction of 1No. Six Classroom Block each at Ehwere Grammar School, Agbarho and Odovie Primary School, Odovie and Supply of 282 Students’ and 26 Teachers’ Furniture, Ughelli North LGA | 13390700000 | Carson Development Ltd No. 1 Ezena Str., Off Ugbor Rd, Benin-City | 2017 | 6 Months after award | 98000000 | 73% | 71218766.81 | 26781233.19 | Ughelli North | On-going
130 | 492 | Renovation of 1No. Six (6) Classroom Block (Block I), 1No. Six (6) Classroom Block (Block II) and Supply of 50 Students’ Desk and 10 Teachers’ Furniture at Afiesere Secondary School | 13390700000 | Dibo Dolor Nigeria Enterprises, Plot 22A, Block 4, Phase 4, Core Area, Asaba | 2017 | 6 Months after award | 46732054.63 | 100% | 43807020.42 | 2925034.21 | Ughelli North | Completed
131 | 517180032 | Renovation of 1No.4 Classroom Block, Renovation of 1No.6 classroom block. Renovation/Rehabilitation of 1No.3 Classroom Block, Renovation of Administrative Block and Renovation of Toilet Block at Otokutu Grammar School, Otokutu, Ughelli South LGA | 13390700000 | Fabock Ventures Flat 4 Mcmerg Estate Summit Road, Asaba | 2017 | 6 Months after award | 67795465.05 | 100% | 63938154.17 | 3857310.88 | Ughelli North | Completed
132 | 517180032 | Supply of 111 Students Desks and 425 Teachers Table and Chairs at Otokutu Grammar School, Otokutu, Ughelli South LGA | 13390700000 | Danike Global Resources, No. 71 Textile Mill Road Benin City | 2017 | 6 Months after award | 6814500.01 | 100% | 0 | 6814500.01 | Ughelli South | Completed
133 | 183 | Construction of Administrative Block and Supply of 48 student’s and 18 teacher’s Furniture at Owhawha Secondary School, Otor-Owhawha, Ughelli South LGA | 13390700000 | Kika-Dan Global Ventures No. 5 Apostolic Str., Okpanam Rd, Asaba | 2017 | 6 Months after award | 39759911.32 | 100% | 33942345.72 | 5817565.6 | Ughelli South | Completed
134 | 521 | Reconstruction of Principal’s Quarters, Construction of Science Laboratory Building and Supply of 120 Students’ and 20 Teachers’ Furniture at Oviri-Olomu Secondary School, Oviri-Olomu, Ughelli South LGA | 13390700000 | Blue Rite Nigeria Limited, 12, Olomoro Road, Isoko South | 2017 | 6 Months after award | 38810456.16 | 100% | 4503481.01 | 34306975.15 | Ughelli South | Completed
135 |  | Renovation of Eight (8) Classroom Block with a separate toilet block with overhead tank (1000 Litres) and (3.5KVA) Sumec generating set. Renovation of two (2) Classroom Block. Supply of 200 student and teachers furniture Erection os School sign post with new Delta State Govt. Logo at Asamana Primary School, Arhavwarien, Ughelli South LGA | 13390700000 | Oroh Gold Nigeria Enterprises, No. 11, Ibadan Road, Steel Town I, D.S.C, Warri | 2017 | 6 Months after award | 55778797.68 | 100% | 52989857.78 | 2788939.9 | Ughelli South | Completed
136 | 498 | Reconstruction/Completion of Six (6) Classroom Block, Renovation of 5 classroom Block, Block wall Fence and Gate house and Supply of 151 Students’ and 10 Teachers’ Furniture at Orhowhe Primary School, Edjophe, Ughelli South LGA | 13390700000 | Baljeesy Integrated Services, 2, Salem Avenue, Infant Jesus, Asaba | 2017 | 6 Months after award | 48600219 | 100% | 28989268.83 | 19610950.17 | Ughelli South | Completed
137 | 517180031 | Renovation of 3No. Four classroom block, Administrative Block, Principals’ quarters, Construction of a block of six toilets, sinking of borehole, Construction of steel stanchion and supply of 40 students’ and 24 teachers’ Furniture at Gbaregolor Secondary School, Gbaregolor, Ughelli South LGA | 13390700000 | Richland Continental Company No. 42 Cemetry Road, Warri | 2017 | 6 Months after award | 98200000 | 100% | 9550000 | 88650000 | Ughelli South | Completed
138 | 517180013 | Renovation of 1No. Seven (7) Classroom Block, Examination and Staff room Block, Supply of 140 Students’ desks and 20 Teachers’ Furniture and Erection of School signboard with State Government Logo at Akashiede Girls Secondary School, Obiaruku, Ukwuani LGA | 13390700000 | Steves Azu & Company, No. 49, Okobi Street, Owa. | 2017 | 6 Months after award | 39552520.84 | 100% | 28058786.17 | 11493734.67 | Ukwuani | Completed
139 | 501 | Renovation of 1No. Five (5) Classroom Block with two offices, 1No. Three (3) Classroom Block without Offices, 1No. Seven (7) Classroom Block without office and 1No. Three (3) Classroom Block without Offices at Model Primary School Obiaruku and Emeni Primary School, Ukwuani LGA | 13390700000 | Danike Global Resources Ventures, 50, Josephine Nwaka Street, Okpanam Road, Asaba | 2017 | 6 Months after award | 49000000 | 100% | 36291003.29 | 12708996.71 | Ukwuani | Completed
140 | 517180031 | i. Construction of Perimeter Fence at Ebedei Secondary School, Ebedei ii. Renovation of 1No. Six classroom block with two offices and provision of 282 students’ and 26 teachers’ furniture, Demolition and Reconstruction of Administrative Block, Renovation of 2 classroom block with 2 offices at Umutu Mixed Secondary School, Umutu, Ukwuani iii. Supply of 332 Students’ and 40 Teachers’ furniture to Selected Schools in Ukwuani LGA | 13390700000 | Afro-Atlantic Global Corporate Ltd., No.5, Dream Court 2, Chevy View Estate, Chevron, Lagos | 2017 | 6 Months after award | 98000000 | 100% | 20000000 | 78000000 | Ukwuani | Completed
141 | 517180030 | Renovation of Laboratory Block at Urhobo College, Effurun, Uvwie | 13390700000 | A.U. Bismack & Associates, No. 6, Nwokobia Street, Asaba | 2017 | 6 Months after award | 24433349.45 | 100% | 6108337.36 | 18325012.09 | Uvwie | Completed
142 | 517180030 | Demolition/Renovation of Hostel Block at Urhobo College, Effurun, Uvwie | 13390700000 | A.U. Bismack & Associates, No. 6, Nwokobia Street, Asaba | 2017 | 6 Months after award | 30307311.89 | 100% | 7576827.97 | 22730483.92 | Uvwie | Completed
143 | 517180030 | Renovation of 1No. ten (10) Classroom (Storey Building) Block at Urhobo College, Effurun, Uvwie | 13390700000 | The Ecclessias Ventures, Sam Obi’s compound, off Efeizomor Street, Boji-Boji, Owa. | 2017 | 6 Months after award | 16421657.92 | 100% | 14853384.89 | 1568273.03 | Uvwie | Completed
144 | 517180030 | Renovation of Administrative Block at Urhobo College, Effurun, Uvwie | 13390700000 | Bob 4 Bob Ventures, 6, Jeddo/Ughoton Road, Jeddo | 2017 | 6 Months after award | 18530007.9 | 40% | 4632501.98 | 13897505.92 | Uvwie | On-going
145 | 517180030 | Renovation of Principals’ Quarters (Storey Building) at Urhobo College, Effurun, Uvwie | 13390700000 | Nefe Austine Nigeria Enterprises, No.124, Okoribi Street, Effurun | 2017 | 6 Months after award | 19274206.33 | 100% | 19274206.33 | 0 | Uvwie | Completed
146 | 517180030 | Renovation of a Storey Building of Eight Classrooms and Offices at Urhobo College, Effurun, Uvwie | 13390700000 | Kinky Homes, 18, Owa Ekei Rd, Agbor | 2017 | 6 Months after award | 36322384.74 | 100% | 36322384.74 | 0 | Uvwie | Completed
147 | 517180030 | Renovation of Perimeter Fence at Urhobo College, Effurun, Uvwie | 13390700000 | Pat-Gone Enterprises, No. 11, Egone Avenue, Ekuigbo, Ughelli | 2017 | 6 Months after award | 24903189.76 | 10% | 6225797.44 | 18677392.32 | Uvwie | On-going
148 | 517180030 | Renovation/Rehabilitation of school dining hall at Urhobo College, Effurun, Uvwie | 13390700000 | Emimarvis Global Resources, No. 22 Redeemers Street, off Mariam Babangida Road, Asaba. | 2017 | 6 Months after award | 29204492.49 | 100% | 7301123.17 | 21903369.32 | Uvwie | Completed
149 | 517180030 | Renovation of twelve (12) classroom block and Vice Principals’ Quarters’ at Urhobo College, Effurun, Uvwie | 13390700000 | Brytex Precision Services, No. 19, Ovwori Street, Ekpan, Delta State | 2017 | 6 Months after award | 31485045.96 | 100% | 7861261.49 | 23623784.47 | Uvwie | Completed
150 | 502 | Construction of prototype six classroom block with store and toilet facilities to upland communities, perimeter fencing of 200m with gate and security house and erection of school sign post with new Delta State logo at Adult Literacy Centre, Ekpan, Uvwie | 13390700000 | Brytex Precision Services, No. 19, Ovwori Street, Ekpan, Delta State | 2017 | 6 Months after award | 50000000 | 100% | 43297327.72 | 6702672.28 | Uvwie | Completed
151 | 517180031 | Construction of 1No. Six Classroom Block and Supply of 282 Students’ and 26 Teachers’ Furniture each at Ebrumede Primary and Secondary Schools, Ebrumede, Uvwie | 13390700000 | Danike Global Resources Venture No. 71, Textile Mill Road, Benin City | 2017 | 6 Months after award | 98000000 | 50% | 24500000 | 73500000 | Uvwie | On-going
152 | 496 | Rehabilitation of Headmistress block, library block, three (3) classroom block without offices and construction of toilet block at Akwarajor Primary School, Koko, Warri North LGA | 13390700000 | Ewejobat Company, 12 Lagos Street, Benin City | 2017 | 6 Months after award | 49000000 | 100% | 12250000 | 36750000 | Warri North | Completed
153 | 517180031 | Construction of 1No. 3 Classroom Block with offices and toilets at Ogheye-Dinigun Primary School, Ogheye, Warri North LGA | 13390700000 | Emonas Integrated Resources Limited, 2 Dafiafiaghor M. Okpako Str., Asaba | 2017 | 6 Months after award | 27089409.38 | 50% | 6772352.35 | 20317057.03 | Warri North | On-going
154 | 517180031 | Construction of 1 No.3 classroom block with offices and toilets each at Abokunwa Primary School, Eghoro and Dudu Primary School, Obonteghareda and supply of 230 students’ and 13 teachers’ furniture to Warri North LGA | 13390700000 | Omitelojor Ventures, No.22 Redeemers’ Street, off Mariam Babangida Road, Asaba. | 2017 | 6 Months after award | 63157938.75 | 50% | 8979120 | 54178818.75 | Warri North | On-going
155 | 499 | Renovation of Two Classroom Block, Four (4) Classroom Block with store, 1No five (5) Classroom Block with store, Twelve (12) Classroom one Storey Block, Ten (10) unit Toilet Block, Twelve (12) unit Toilet block, Proposed Fence and Gate-house 16-20 Metres and Supply of 523 Student’s and 61 Teachers’ Furniture at Agbeje P/S, Ugbuwangue, Warri South LGA | 13390700000 | Jomay Resources Ventures, 47, Agboghoroma Way, Sapele | 2017 | 6 Months after award | 49500000 | 100% | 42797400 | 6702600 | Warri South | Completed
156 | 526 | Renovation/ Rehabilitation of Collapsed portion of School fence, Plumbing & mechanical works, Supply of Laboratory Equipment and 25 Teachers’ and 400 Students’ Furniture at Dore-Numa College, Warri, Warri South LGA | 13390700000 | Dere Integrated Resources, 12 Andy uwejeyan Crescent, Asaba | 2017 | 6 Months after award | 39234068 | 100% | 37790487.6 | 1443580.4 | Warri South | Completed
157 | 527 | Rehabilitation/Conversion of Six (6) Classroom Block to Examination Hall and supply of 10 Teachers’ and 220 Students’ Furniture at Ubeji Grammar School, Warri, Warri South LGA | 13390700000 | Danbes Corporate Venture, 44, Ekpen Street, Okere, Warri | 2017 | 6 Months after award | 39774789.12 | 100% | 31257909.12 | 8516880 | Warri South | Completed
158 | 517180031 | Reconstruction of 1 No. Block of six (6) classrooms with stores and toilet (Block B), 1 No. Block of 2 Classrooms with office (Block C), 1 No. block of 2 classrooms with office (Block D) and supply of 951 students’ and 100 teachers’ furniture at Agbassa Primary School, Warri, | 13390700000 | Danike Global Resources Ventures, 50, Josephine Nwaka Street, Okpanam Road, Asaba | 2017 | 6 Months after award | 99500000 | 60% | 24875000 | 74625000 | Warri South | On-going
159 | 517180031 | i. Renovation of 1 No. 6 Classroom Block with office, 1 No. 3 classroom Laboratory Block with office, 2 No. 3 classroom block with office at Erejuwa Grammar School, Ode-Itsekiri ii. Supply of 479 students and 35 Teachers Furniture, Warri South I | 13390700000 | Ani Corporate International Limited, Flat 1, Block B, Gidado Idris Wuse, Abuja | 2017 | 6 Months after award | 99977774.09 | 100% | 59986664.45 | 39991109.64 | Warri South | Completed
160 | 510 | Reconstruction of Prototype Six (6) Classroom Block with Stores and Toilet Facilities at Omaretsosene Primary School, Ogidigben, Warri South West LGA | 13390700000 | Congosco Enterprises Limited 1, Temile Close, by DDPA, NPA, Expresss, Warri | 2017 | 6 Months after award | 48500000 | 60% | 12125000 | 36375000 | Warri South West | On-going
161 | 517180013 | Rehabilitation of 1No. Six Classroom Block with offices, Construction of Gate House, Toilet and Supply of 10 Teachers’ and 39 Students’ Furniture at Omaretsosene Primary School, Ogidigben, Warri South West LGA | 13390700000 | Bluetel Multy Concept 2, Eyone Godwin Link Road, Ugbunwangue | 2017 | 6 Months after award | 44800000 | 60% | 11200000 | 33600000 | Warri South West | On-going
162 | 517180031 | Renovation of 3 No. 6 classroom block and supply of 401 students’ and 30 teachers’ furniture at Ewein Primary School II, Ogbe-Ijoh, Warri South West LGA | 13390700000 | Danike Global Resources Ventures, 50, Josephine Nwaka Street, Okpanam Road, Asaba | 2017 | 6 Months after award | 99980035.95 | 55% | 24995008.99 | 74985026.96 | Warri South West | On-going
163 | 517180020 | Construction of 1No. Hostel Block in Riverine Communities in the State at Kokodiagbene Secondary School, Kokodiagbene, Warri South West LGA | 13390700000 | Eles-Mere Corporate Services, Plot 21 Neimogha Avenue, DDPA Estate, Effurun | 2017 | 6 Months after award | 83000000 | 50% | 20750000 | 62250000 | Warri South West | On-going
|  | TOTAL |  |  |  |  | 7770086536.34 |  | 4749873887.96 | 3020212648.38

## 2018
DELTA STATE PPC FORM: ANNUAL PROCUREMENT PLAN FOR PROCURING ORGANIZATIONS NAME OF PROCURING ORGANISATION: MINISTRY OF BASIC AND SECONDARY EDUCATION (2019)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
S/N | SUB-HEAD | PROJECT DESCRIPTION | APPROVED 2018 BUDGET (CAPITAL) | NAME OF CONTRACTOR | YEAR OF AWARD | EXPECTED DATE OF COMPLETION | CONTRACT SUM | % OF JOB COMPLETION | AMOUNT PAID TO DATE | OUTSTANDING PAYMENT | LGA | PROJECT STATUS
3 | 37 | Renovation/rehabilitation of laboratory block at Model Secondary School, Onich-Olona, Aniocha North LGA. | 20158343185 | Januels Resources Links, No.6 Chinonso Unini Crescent, off Okpanam Road, Asaba. | 2019 | 6 Months after award | 16338482.19 | 100% | 4084620.55 | 12253861.64 | Aniocha North | Complete
5 | 490 | Renovation of 1No.6 classroom block with 6No. offices, 1No.6 classroom block with 1No. office and supply of 17 pupils’ and 4 teachers’ furniture at Iyiogbe Primary School, Onicha-Olona, Aniocha North LGA. | 20158343185 | Emtina Impex Services, 3, Leo Okogwu Street, Asaba. | 2019 | 6 Months after award | 49485515.42 | 100% | 37000000 | 12485515.42 | Aniocha North | Complete
7 |  | Renovation of 1No.5 classroom block, supply of 110 students’ and 15 teachers’ furniture and erection of standard school signpost at Enuofu Primary School, Issele-Mkpitime and supply of 100 teachers’ and 540 students’ furniture to Public Schools in Aniocha North LGA. | 20158343185 | Fidelity Fortune Global Enterptrises, 3, Fidelity Fortune Street, off Summit Road Asaba | 2019 | 6 Months after award | 48235702.32 | 100% | 12058925.58 | 36176776.74 | Aniocha North | Complete
8 | 549 | i. Renovation of 6 classroom block and erection of standard school signpost at Kadinma Primary School, Onicha-Uku, ii. supply of 190 students’ and 15 teachers’ furniture at Adams Primary School, Issele-Uku, iii. supply of laboratory equipment at Onicha-Ugbo Mixed Secondary School,Onicha-Ugbo, iv. supply of laboratory equipment and 15 teachers’ and 65 students’ furniture at Ugbodu Secondary School, Ugbodu in Aniocha North LGA. | 20158343185 | Ubrete Resources, 6, Chidinma Drive, off Clement Okolie Drive, Asaba | 2019 | 6 Months after award | 47733540.43 | 50% | 0 | 47733540.43 | Aniocha North | On-going
14 | 490 | Renovation of 1No.6 classroom block (Block A), 1No.6 classroom block (B) and supply of 156 students’ and 20 teachers’ furniture at Nsukwa Grammar School, Nsukwa, Aniocha South LGA. | 20158343185 | Adobrite Enterprises, 19, Joel Felix Drive, off Okpanam Road, Asaba. | 2019 | 6 Months after award | 49466941.12 | 0% | 0 | 49466941.12 | Aniocha South | On-going
15 | 368 | Construction of prototype 1No.6 classroom block with stores and toilet facilities, toilet block with borehole and water reticulation and erection of school signpost with Delta State logo at Olloh Mixed Secondary School, Olloh, Ogwashi-Uku, Aniocha South LGA. | 20158343185 | KK & Jamie Enterprises No.22, Raphael Obianke | 2019 | 6 Months after award | 50170700 | 0% | 0 | 50170700 | Aniocha South | On-going
17 | 177 | Renovation of 1No.6 classroom block with attached offices at Ubulu-Uno M/S/S, Ubulu-Uno, Aniocha South LGA | 20158343185 | Thixo Affairs Enterprises, 8, Otuogwu Street, Asaba | 2019 | 6 Months after award | 27417860.34 | 50% | 0 | 27417860.34 | Aniocha South | On-going
19 | 177 | Renovation/rehabilitation of 1No.4 classroom block with 6No.offices and 1No.3 classroom block with attached offices and toilets at Ubulu-Uno M/S/S, Ubulu-Uno, Aniocha South LGA | 20158343185 | Onye Contract and Trading Ent. 24, Ifeanyichukwu Street Opp. Infant Academy, Asaba | 2019 | 6 Months after award | 33582139.66 | 80% | 0 | 33582139.66 | Aniocha South | On-going
20 | 490 | Renovation of 1No.6 classroom block with offices and toilets, 1No.3 classroom block with 2No. offices and supply of 195 students’ desk and 30 teachers’ furniture at Adaigbo Secondary School, Aniocha South LGA | 20158343185 | Sumi Enterprises Plot 6, Block 2, Core Area, Asaba | 2019 | 6 Months after award | 39945131.32 | 0% | 0 | 39945131.32 | Aniocha South | On-going
21 | 368 | Renovation of 1No.3 classroom block, 1No.6 classroom block with office and toilet and construction of 1No. Administrative block (small size) at Egbudu Mixed Secondary School, Egbudu-Akah, Aniocha South LGA | 20158343185 | Venski Ventures, 32 Summit Road, Asaba. | 2019 | 6 Months after award | 47949000 | 0% | 0 | 47949000 | Aniocha South | On-going
22 | 368 | Supply of 300 Students’/pupils’ double desks and 100 Teachers’ Furniture to Selected Schools, Bomadi LGA | 20158343185 | Vetic Nig. Enterprises, 12, Onyekosor Street, Off Marble Hill School, Okpanam | 2019 | 6 Months after award | 16104000 | 100% | 16104000 | 0 | Bomadi | Complete
27 | 490 | Demolition of 1No.4 classroom block, construction of 1No.5 classroom block and supply of 94 students furniture at Kpakiama Secondary School, Kpakiama, Bomadi LGA | 20158343185 | KK & Jamie Enterprises No.22, Raphael Obianke Street, Boji Boji Owa, Agbor. | 2019 | 6 Months after award | 39640448.33 | 100% | 0 | 39640448.33 | Bomadi | Complete
28 | 368 | Supply of 100 Students and 15 Teachers’ Furniture to Ogbolubiri Secondary School, Ogbeingbene, Burutu LGA | 20158343185 | B&D Construction Enterprise, 2, Asupa Street, Edjeba, Warri | 2019 | 6 Months after award | 4460500 | 100% | 4460500 | 0 | Burutu | Complete
29 | 4 | Construction of 1No. Six (6) Classroom Block with offices (Semi Riverine) at Ogbolubiri Secondary School, Burutu | 20158343185 | Warri Hass (Nigeria) Company, 8, Korobiri Quarters, Bomadi Town, Bomadi | 2019 | 6 Months after award | 42085975.04 | 100% | 39240528.49 | 2845446.55 | Burutu | Complete
31 | 490 | Renovation of 1No. 6 Classroom Block with Offices and a U shaped Classroom Block with offices at Ofou Primary School, Burutu LGA | 20158343185 | Borosugha Ventures, 13D, Lokoja Street, DSC, Ovwian Aladja | 2019 | 6 Months after award | 39859640.35 | 100% | 37491348.99 | 2368291.36 | Burutu | Complete
36 | 490 | Reconstruction of 1No.4 classroom block, renovation of 1No.4 classroom block with office and supply of 20 teachers’ and 82 students’ furniture, Tamigbe Grammar School, Burutu | 20158343185 | P. A. Finchley Enterprises, No. 54, Razaq Balogun Street, Off Adeniran Ogunsanya, Surulere, Lagos | 2019 | 6 Months after award | 39991835 | 25% | 9997958.75 | 29993876.25 | Burutu | On-going
37 | 368 | Construction of Students’ Toilet and Examination Hall at Ejaife Primary School, Okpara-Inland, Ethiope East LGA | 20158343185 | Oruese International, Nigeria Enterprises Plot 27/28 DDPA Housing Estate, Ikoyo Avenue, Sapele | 2019 | 6 Months after award | 38000000 | 100% | 0 | 38000000 | Ethiope East | Complete
38 | 477 | Contract for the construction of block wall fence with reinforced strip foundation and ground beam and erection of school signpost with Delta State logo at Orhoakpor Secondary School, Orhoakpor, Ethiope East LGA. | 20158343185 | Flo Palms Enterprises | 2019 | 6 Months after award | 49183229.48 | 73% | 36096921.88 | 13086307.6 | Ethiope East | On-going
40 | 368 | Supply of 350 Students’/pupils’ double desks and 150 Teachers’ Furniture to Selected Schools, Ethiope East LGA | 20158343185 | Fidborin Nigeria Enterprises, 111, Elibujor Road, DLA, Asaba | 2019 | 6 Months after award | 20438000 | 25% | 5109500 | 15328500 | Ethiope East | On-going
45 | 490 | Renovation/rehabilitation of 1No. 12 classroom block at Urhegbe Primary School, Okpara-Inland, Ethiope East LGA | 20158343185 | Onye Contract and Trading, No. 21 Ifeanyichukwu Nwagbo Street, Opp. Infant Jesus Academy, Asaba. | 2019 | 6 Months after award | 39208914.31 | 45% | 9802228.58 | 29406685.73 | Ethiope East | On-going
47 | 490 | Renovation/rehabilitation of 1No.4 classroom block, school hall with offices, stores and toilet facilities, construction of students’ toilet with water stanchion and borehole and supply of 170 students’ and 10 teachers’ furniture at Agbon Secondary School, Isiokolo, Ethiope East LGA. | 20158343185 | Flo Palms Enterprises, 1, Chime Avenue, New Haven, Enugu | 2019 | 6 Months after award | 49200000 | 25% | 12300000 | 36900000 | Ethiope East | On-going
48 | 549 | Renovation of 1No. 7 classroom block with offices, a block of 4 classroom, 3 classroom block with a separate toilet of 4No. units, Supply of 120 students’ and 15 teachers’ furniture (for 214 pupils) and Erection of standard school sign post (with the name of the school and the new State logo) at Urhuovie Primary School, Abraka, Ethiope East LGA | 20158343185 | Peabody Terrace Enterprises, House 1-38, Road 20, Victoria Garden City, Ajah, Lagos | 2019 | 6 Months after award | 45600273.94 | 25% | 11400068.34 | 34200205.6 | Ethiope East | On-going
50 | 368 | Renovation/rehabilitation of 1No.5 classroom block and renovation/conversion of existing hall to a 4 classroom block at Igun Secondary School, Igun, Ethiope East LGA | 20158343185 | J-Hova World Enterprises 8, Otuogwu Street, Asaba | 2019 | 6 Months after award | 32581655.89 | 0% | 0 | 32581655.89 | Ethiope East | On-going
51 | 368 | Renovation of laboratory block and Erection of standard school signboard (with the name of the school and the new State logo) at Ukavbe Secondary School, Otefe, Oghara, Ethiope West LGA. | 20158343185 | Uppington Global Services, 39, Isiaye Drive, Asaba. | 2019 | 6 Months after award | 22876616.38 | 100% | 20960735.79 | 1915880.59 | Ethiope West | Complete
52 | 368 | Construction of a prototype 1No. Six (6) classroom block with stores and toilet facilities and Erection of State Government Branding uniform Project signboard at Uduaka Secondary School, Mosogar, Ethiope West LGA. | 20158343185 | Richman and Randy Enterprises, 44, Sediko Road, Effurun | 2019 | 6 Months after award | 38315137.09 | 40% | 9578784.27 | 28736352.82 | Ethiope West | On-going
53 | 517180030 | Construction of a prototype 1No. six classroom block with stores and toilet facilities and Erection of Standard School Sign Post (with the name of the School and the new State Logo) at Uduaka Secondary School, Mosogar, Ethiope West LGA. | 20158343185 | Okevwe Koro Enterprises, 5, Ighoyota Avenue, Mosogar | 2019 | 6 Months after award | 38410137.09 | 50% | 9602534.27 | 28807602.82 | Ethiope West | On-going
56 | 368 | Supply of 500 students’ furniture to Uduaka Secondary School, Mosogar, Ethiope West LGA. | 20158343185 | Bawo Global Resources, Plot 120B, 5th Road DDPA Estate, Asaba. | 2019 | 6 Months after award | 19710000 | 100% | 4927500 | 14782500 | Ethiope West | Complete
57 | 490 | Renovation/rehabilitation of 1No.3 classroom block with offices and toilet, a block of 1 classroom with hall and offices, construction of a prototype administrative block and supply of 127 student desk and 38 teachers’ furniture at Osoguo Secondary School, Jesse, Ethiope West LGA. | 20158343185 | Obuseme Global Enterprise, No.54, Kogoro Street, Sapele. | 2019 | 6 Months after award | 49400000 | 50% | 12350000 | 37050000 | Ethiope West | On-going
60 | 368 | Renovation/rehabilitation of 1No.4 laboratory block with offices and tooilets and 1No.3 classroom block at Oreki Secondary School, Oghareki, Ethiope West LGA. | 20158343185 | Neonac Nuel Nigeria Enterprises No.63, Tete Street, Boji Boji Owa. | 2019 | 6 Months after award | 39727697.5 | 100% | 35754972.75 | 3972724.75 | Ethiope West | Complete
61 | 368 | Renovation of 1No.6 classroom block, reconstruction of 1No.3 classroom block, renovation/rehabilitation of 1No.3 classroom block with office, construction of prototype students’ toilet (including water borehole and erection of standard school signpost with State logo at Ekumagba Primary School, Ugbenu, Koko Junction, Oghara, Ethiope West LGA. | 20158343185 | Ubrete Resources 2, Aretha Table Water Road, Asaba. | 2019 | 6 Months after award | 49475967 | 0% | 0 | 49475967 | Ethiope West | Complete
63 | 368 | Supply of 450 Students’ and 46 teachers’ furniture to Efeizomor Secondary School, Boji Boji Owa, Ika North East LGA | 20158343185 | Chovis Multi Links, 2, Olatunji Street, Lagos | 2019 | 6 Months after award | 18662400 | 0% | 0 | 18662400 | Ika North East | On-going
65 | 368 | Construction of Administrative block and Erection of Standard School Sign Post (with the name of the School and the new State Logo) at Owa-Ofie Secondary School, Owa-Ofie, Ika North East LGA | 20158343185 | Hubert Igwe (Nigeria) Enterprises, 56, Obaigbena Street, B.B. Owa | 2019 | 6 Months after award | 25326481.29 | 100% | 0 | 25326481.29 | Ika North East | Complete
66 | 368 | Construction of 6 classroom block with stores and toilet facilities at Owa-Ofie Secondary School, Owa-Ofie, Ika North East LGA | 20158343185 | J.K.M Ventures, 38, Opia Street, Boji-Boji, Owa | 2019 | 6 Months after award | 38135137.09 | 85% | 0 | 38135137.09 | Ika North East | On-going
67 | 368 | Supply of 200 Students’ and 50 Teachers’ Furniture to Owa-Ofie Secondary School, Owa-Ofie, Ika North East LGA | 20158343185 | De Mustard Seed System Services, 6, Abiamuwe Street, Umunede | 2019 | 6 Months after award | 9717601.62 | 0% | 0 | 9717601.62 | Ika North East | On-going
70 | 368 | Supply of 150 students’ and 20 teachers’ furniture at Comprehensive High School Igbodo, Ika North East LGA. | 20158343185 | Innapo Ventures, 17, Gbenga Street, Agbor | 2019 | 6 Months after award | 6458400 | 100% | 0 | 6458400 | Ika North East | Complete
71 | 368 | Construction of prototype teachers’/students’ toilet, electricity connection to BEDC mains and renovation of examination hall at Comprehensive High School, Igbodo, Ika North East LGA | 20158343185 | Udokanma Global Ent. 6, Dan Ikem Street, Umunede. | 2019 | 6 Months after award | 42311837.38 | 100% | 0 | 42311837.38 | Ika North East | Complete
72 | 368 | Construction of prototype administrative block (small size) and supply of 67 students’ and 15 teachers’ furniture and erection of standard school sign post (with the name of the school and the new State logo) at Osimi Primary School, Owanta-Aliosimi, Ika North East LGA | 20158343185 | Hubert-Igwe (Nigeria) Enterprises, 56, Obaigbena Street, Boji Boji Owa | 2019 | 6 Months after award | 19053601.09 | 100% | 0 | 19053601.09 | Ika North East | Complete
76 | 177 | Construction of administrative block and staff room at Efeizomor Secondary School, Boji Boji Owa, Ika North East LGA | 20158343185 | Eric Kings Ventures, 21 Omi Street Owa-Alero | 2019 | 6 Months after award | 25146481.29 | 100% | 0 | 25146481.29 | Ika North East | Complete
78 | 368 | Renovation of 1no. Six (6) Classroom Block with attached office at Diagbor Primary School, Owerre-Olubor, Ika North East LGA | 20158343185 | Sumi Enterprises, Plot 6, WAEC Road, Core Area, Asaba | 2019 | 6 Months after award | 20404890.48 | 0% | 0 | 20404890.48 | Ika North East | On-going
79 | 49 | Supply of 400 Students’ and 180 Teachers’ Furniture to Selected Schools, Ika North East LGA | 20158343185 | Rosen Integrated Services, 11, Isichei Close, Owa | 2019 | 6 Months after award | 23782000 | 100% | 0 | 23782000 | Ika North East | Complete
80 | 47 | Renovation of 1No. 3 classroom block, 1No.6 classroom block and erection of standard school sign post (with the name of the school and State logo) at Aghaulor Primary, Ute-Okpo, Ika North East LGA | 20158343185 | Ewere Ventures, 49A Owerri/Enugu Road, Ute-Okpu, Agbor. | 2019 | 6 Months after award | 28123161.62 | 65% | 7030790.41 | 21092371.21 | Ika North East | On-going
81 | 47 | Renovation of 1 No.6 classroom block with office at Aghaulor Primary, Ute-Okpo, Ika North East LGA | 20158343185 | Zuru-Elohor Enterprises, 46, Efeizomor Street, Boji Boji Owa | 2019 | 6 Months after award | 15677410.59 | 65% | 0 | 15677410.59 | Ika North East | On-going
82 | 47 | Supply of 80 students’ and 20 teachers’ furniture at Aghaulor Primary, Ute-Okpo, Ika North East LGA | 20158343185 | Sharpton Enterprises 41, Atinuke Olabanjo Street, Ikeja | 2019 | 6 Months after award | 3892320 | 100% | 3892320 | 0 | Ika North East | Complete
83 | 368 | Renovation of 1No. Four (4) Classroom Block with attached 4No. offices, Renovation of 1No. Three (3) Classroom Block with attached Headmasters’ office and staffroom at Ebueno Primary School, Owa-Alidinma, Ika North East LGA | 20158343185 | Solo Royal Ventures, 61, Convent Street, Boji-Boji, Owa | 2019 | 6 Months after award | 24339787.78 | 100% | 0 | 24339787.78 | Ika North East | Complete
85 | 490 | Reconstruction of 1No.6 classroom block with offices and toilets and construction of water borehole and reticulation at Owanta Secondary School, Owanta, Ika North East LGA | 20158343185 | Eric Kings Ventures 21 Omi Street Owa-Alero | 2019 | 6 Months after award | 49479137.86 | 50% | 0 | 49479137.86 | Ika North East | On-going
86 | 277 | Renovation/rehabilitation of 1No.4 classroom block, 1No.2 classroom block, construction of students’ toilet (prototype), construction of water supply scheme and erection of standard school signpost with the name of the school and State Government logo at Ute-Alohen Primary School, Ute-Alohen, Ika North East LGA. | 20158343185 | Bar Zigzag and Lounge Enterprise, No.4 Thankgod Crescent, Boji Boji Owa, Agbor | 2019 | 6 Months after award | 43900000 | 85% | 0 | 43900000 | Ika North East | On-going
87 | 549 | Renovation/rehabilitation of 1No.6 classroom block (block A), 1No.6 classroom block with offices (block B) and supply of 53 students’ and 15 teachers’ furniture at Emuhu Mixed Secondary School, Emuhu and supply of 15 teachers’ and 120 students’ furniture at Ekwuoma Mixed Secondary School, Ekwuoma, Ika North East LGA. | 20158343185 | Ozick Contractors, 67, Okpe Road, Sapele | 2019 | 6 Months after award | 49672657.77 | 100% | 0 | 49672657.77 | Ika North East | Complete
88 | 490 | Construction of 1No.6 classroom block with offices and walkway at Command Secondary School, Mbiri, Ika North East LGA. | 20158343185 | Femmak and Company | 2019 | 6 Months after award | 38842789.83 | 100% | 38842789.83 | 0 | Ika North East | Complete
89 | 49 | Supply of 110 students’ double seater desks and 20 teachers’ furniture at Ute-Ogbeje Secondary School, Ute-Ogbeje, Ika North East North LGA | 20158343185 | Neonac Nuel Nigeria Enterprises, No.63, Tete Street, Boji Boji Owa. | 2019 | 6 Months after award | 4750000 | 100% | 4750000 | 0 | Ika North East | Complete
92 | 490 | Demolition/reconstruction of administrative block, renovation of 1No.3 classroom block and supply of 53 students’ and 10 teachers’ furniture at Ute-Okpu Grammar School, Ute-Okpu, Ika North East LGA | 20158343185 | Ve-Man Global Enterprises 104, Okpanam Road, Asaba. | 2019 | 6 Months after award | 39960480.95 | 100% | 39960480.95 | 0 | Ika North East | Complete
93 | 49 | Supply of 400 Students’ and 180 Teachers’ Furniture to Selected Schools, Ika South LGA | 20158343185 | Bernalim Ent. Plot 141 Phase v, Core Area, Asaba | 2019 | 6 Months after award | 23782000 | 100% | 0 | 23782000 | Ika South | Complete
95 | 190 | General External Works at Igumbor-Otiku Secondary School, Agbor, Ika South LGA | 20158343185 | Toppet Nigeria Ent. Plot 12, Block II, DDPA Housingg Estate, Asaba | 2019 | 6 Months after award | 29983351.61 | 0% | 29983351.61 | 0 | Ika South | On-going
97 | 368 | Supply of 350 students’ and 35 teachers’ furniture to Igumbor-Otiku Secondary School, Agbor, Ika South LGA | 20158343185 | J.O. Emenim Enterprises (Nigeria), Idumu Eku Farm Road, Okpe Abavo, Delta State. | 2019 | 6 Months after award | 14496300 | 100% | 14496300 | 0 | Ika South | Complete
98 | 368 | Construction of Administrative block and Erection of State Government Branding uniform project signboard at Alihagu Secondary School, Alihagu, Ika South LGA | 20158343185 | Rapier Global services, 53, Prof. John Ebie Street, Agbor | 2019 | 6 Months after award | 25326481.29 | 45% | 0 | 25326481.29 | Ika South | On-going
99 | 49 | Construction of 1No. Six (6) Classroom Block with Stores and Toilets at Alihagu Secondary School, Alihagu | 20158343185 | Machellange Enterprise, 71A, Lafiaji Lane, Dolphin Estate, Ikoyi, Lagos | 2019 | 6 Months after award | 38135137.09 | 45% | 9533784.27 | 28601352.82 | Ika South | On-going
100 | 368 | Construction of 1No. Six (6) Classroom block with stores and toilet facilities and Erection of School signboard with new State Government Logo at Alihagu Secondary School, Alihagu, Ika South LGA | 20158343185 | Gain-Hill Enterprises, Benin-City | 2019 | 6 Months after award | 38410137.09 | 45% | 0 | 38410137.09 | Ika South | On-going
102 | 368 | Renovation of 1 no.4 classroom block with attached cubicles, staff room and administrative offices at Obi-Anyima Secondary School, Obi-Anyima, Ika South LGA | 20158343185 | Bernalim Ent. Plot 141 Phase v, Core Area, Asaba | 2019 | 6 Months after award | 23219278.84 | 50% | 0 | 23219278.84 | Ika South | On-going
103 | 368 | Renovation of 1No. six (6) Classroom Block with attached offices at Obi-Anyima Secondary School, Obi-Anyima, Ika South LGA | 20158343185 | Ajuibili-Igumbor and Sons Enterprises, (Nigeria) 13, Odozi Street, Orogodo, Agbor | 2019 | 6 Months after award | 19963008.5 | 50% | 6388163.08 | 13574845.42 | Ika South | On-going
104 | 368 | Renovation of 1no. three (3) Classroom Block without attached office at Obi-Anyima Secondary School, Obi-Anyima, Ika South LGA | 20158343185 | Emimarvis Global Resources, 22, Redeemers Street, Asaba | 2019 | 6 Months after award | 9683939.52 | 50% | 0 | 9683939.52 | Ika South | On-going
105 | 368 | Renovation of 1No. three (3) Classroom Block with attached 3No. offices and Toilets and Erection of Standard School Sign Post (with the name of the School and the new State Logo) at Obi-Anyima Secondary School, Obi-Anyima, Ika South LGA | 20158343185 | Emimarvis Global Resources, 22, Redeemers Street, Asaba | 2019 | 6 Months after award | 11103838.46 | 100% | 10074051.75 | 1029786.71 | Ika South | Complete
106 | 368 | Supply of 150 Students’ and 20 Teachers’ Furniture to Obi-Anyima Secondary School, Obi-Anyima, Ika South LGA | 20158343185 | Bernalim Ent. Plot 141, Phase V, Core Area, Asaba | 2019 | 6 Months after award | 6447600 | 0% | 0 | 6447600 | Ika South | On-going
107 | 368 | Renovation of 1No. 3 classroom block and attached laboratory block with attached offices at Obi-Anyima Secondary School, Obi-Anyima, Ika South LGA | 20158343185 | J.O. Emenim Enterprises (Nigeria), Idumu Eku Farm Road, Okpe Abavo, Delta State. | 2019 | 6 Months after award | 18055295.1 | 100% | 18055295.1 | 0 | Ika South | Complete
109 | 490 | Renovation/rehabilitation of 1No.6 classroom block with offices and toilet facilities, construction of prototype 1 No. students’ toilet with borehole and water stanchion, supply of 30 students’ furniture and erection of standard school signpost with the name of the school and State logo at Jegbefume Government Secondary School, Abavo, Ika South LGA. | 20158343185 | Jemide Williams, 99, Nnebisi Road, Cable Point, Asaba. | 2019 | 6 Months after award | 39702143.91 | 45% | 9925535.98 | 29776607.93 | Ika South | On-going
110 | 490 | Construction of perimeter block wall fence with gate and gate house , demolition/reconstruction of 1No.3 classroom block with attached offices , renovation/rehabilitation of 1No.3 classroom block and sinking of water borehole, water tank, generating set/water reticulation to buildings/connection of electricity to the mains at Umu P/S, Agbor-Alidinma, Ika South LGA. | 20158343185 | Ozick Contractors, 67, Okpe Road, Sapele | 2019 | 6 Months after award | 49544373.26 | 100% | 47067160.3 | 2477212.96 | Ika South | Complete
114 | 368 | Renovation/rehabilitation of 1No.storey block of 8 classrooms at Charles Burr Primary School, Agbor, Ika South LGA | 20158343185 | Eric Kings Ventures,No. 21 Omi Str., Owa-Alero | 2019 | 6 Months after award | 19844462.47 | 30% | 0 | 19844462.47 | Ika South | On-going
115 | 368 | Renovation/rehabilitation of 1No.4 classroom block at Charles Burr Primary School, Agbor, Ika South LGA | 20158343185 | Unified World Enterprises 22, Ojelade Street, Ikorodu Rd, Yaba, Lagos. | 2019 | 6 Months after award | 13196685.16 | 45% | 0 | 13196685.16 | Ika South | On-going
121 | 490 | Reconstruction of 1No.6 classroom block with offices, 1No.3 classroom block with offices and supply of 180 students’ furniture at Iyede Secondary Commercial School, Iwride-Iyede, Isoko North LGA. | 20158343185 | Uzefav Nig. Ent, No.5, Ogbaide Close, Ugbolokposo, Effurun | 2019 | 6 Months after award | 49508333.54 | 50% | 12377083.39 | 37131250.15 | Isoko North | On-going
125 | 368 | Construction of a prototype 1 No.6 classroom block with stores and toilet facilities at Orie Secondary School, Orie-Irri, Isoko South LGA. | 20158343185 | De Ama Ventures, Block C4, House 4, Kabusa Gardens Estate, Abuja. | 2019 | 6 Months after award | 38135137.09 | 50% | 9533784.27 | 28601352.82 | Isoko South | On-going
126 | 368 | Construction of Administrative block at Orie Secondary School, Orie-Irri, Isoko South LGA. | 20158343185 | Azani & Azani Enterprises, 13B Olutayo Alao Street, River Valley Estat, Ojodu Berger, Lagos | 2019 | 6 Months after award | 25146481.29 | 100% | 0 | 25146481.29 | Isoko South | Complete
127 | 368 | Construction of 1No.6 classroom block and erection of school sign post with State logo at Orie Secondary School, Orie-Irri, Isoko South LGA. | 20158343185 | Innapo Ventures, No.12, Gbenga Street, Agbor | 2019 | 6 Months after award | 38410137 | 80% | 0 | 38410137 | Isoko South | On-going
128 | 368 | Renovation of school hall and provision of water borehole, overhead water stand/tank and generator at Igbide Grammar School, Igbide, Isoko South LGA. | 20158343185 | Ekemena Associates, 2nd Floor, Eku House, Effurun | 2019 | 6 Months after award | 21820085.82 | 40% | 0 | 21820085.82 | Isoko South | On-going
130 | 368 | Renovation of 1 No.6 classroom block with offices and toilets (block 2) at Igbide Grammar School, Igbide, Isoko South LGA. | 20158343185 | Oruese International Nigeria Enterprises, Plot 27/28, DDPA Housing Estate, Ikoyo Avenue, off Shell Road, Sapele | 2019 | 6 Months after award | 33564131.33 | 100% | 0 | 33564131.33 | Isoko South | Complete
134 | 49 | Renovation of 1No.6 classroom block with offices at Umeh Secondary School, Umeh, Isoko South LGA. | 20158343185 | F.B. Supreme Ventures 34, Oleh Road, Irri Town | 2019 | 6 Months after award | 31508465.01 | 100% | 29933042.01 | 1575423 | Isoko South | Complete
137 | 490 | i. Renovation of 1No.3 classroom block and 1No.6 classroom block at Evoja Primary School, Oleh, ii. 1No.3 classroom block and 1No. Hall at Isoko Central Primary School, Oleh and iii. supply of 95 students’ furniture to selected Primary and Secondary Schools in Isoko South LGA | 20158343185 | Adobrite Enterprises 19, Joel Felix Drive, off Okpanam Road, Asaba. | 2019 | 6 Months after award | 49369241 | 45% | 0 | 49369241 | Isoko South | On-going
140 | 368 | Renovation of 1 no. 6 classroom block with stores and toilets (block B) at Iyede - Ame Secondary School, Iyede-Ame, Ndokwa East LGA | 20158343185 | Hopshack Nig Enterprises, 8, Dumebi Amaka Isidi Street, off DLA Road, Asaba. | 2019 | 6 Months after award | 20967268.35 | 70% | 18626276.68 | 2340991.67 | Ndokwa East | On-going
141 | 368 | Supply of 250 Students’/pupils’ double desks and 80 Teachers’ Furniture to Selected schools, Ndokwa East LGA | 20158343185 | Nibveb Contractors, 14, Bola Ogunsanya Crescent, Magodo, GRA, Lagos | 2019 | 6 Months after award | 13255000 | 100% | 0 | 13255000 | Ndokwa East | Complete
142 | 368 | Supply of 200 Students and 20 Teachers’ Furniture to Aboh Secondary School, Aboh, Ndokwa East LGA | 20158343185 | Rose Edjekohwo Enterprises, 1, Ovie Palace Road, Effurun | 2019 | 6 Months after award | 8272800 | 40% | 0 | 8272800 | Ndokwa East | On-going
144 | 368 | Renovation of Principals’ Quarters at Iyede-Ame Secondary School, Iyede-Ame, Ndokwa East LGA | 20158343185 | Waya Numua Ent, 2nd Floor, Copper House, Opp. Abuja High Court, Abuja | 2019 | 6 Months after award | 10311726.08 | 0% | 0 | 10311726.08 | Ndokwa East | On-going
145 | 368 | Renovation of 1No. Six (6) Classroom Block (Block A) at Iyede-Ame Secondary School, Iyede-Ame, Ndokwa East LGA | 20158343185 | Waya Numua Ent, 2nd Floor, Copper House, Opp. Abuja High Court, Abuja | 2019 | 6 Months after award | 24772795.76 | 0% | 0 | 24772795.76 | Ndokwa East | On-going
146 | 368 | Demolition and Reconstruction of Administrative Block at Iyede-Ame Secondary School, Iyede-Ame, Ndokwa East LGA | 20158343185 | Waya Numua Ent, 2nd Floor, Copper House, Opp. Abuja High Court, Abuja | 2019 | 6 Months after award | 30765777.54 | 0% | 0 | 30765777.54 | Ndokwa East | On-going
147 | 368 | Renovation of Administrative Block and Four Classrooms with Stores and Toilets at Aboh Secondary School, Aboh, Ndokwa East LGA | 20158343185 | Tony Uti-Son (Nigeria) Company, 5, Oduduwa Street, Ikate, Surulere, Lagos | 2019 | 6 Months after award | 13770161.31 | 100% | 0 | 13770161.31 | Ndokwa East | Complete
148 | 368 | Renovation of 1No. Four Classroom Block without Stores at Aboh Secondary School, Aboh, Ndokwa East LGA | 20158343185 | Tony Uti-Son (Nigeria) Company, 5, Oduduwa Street, Ikate, Surulere, Lagos | 2019 | 6 Months after award | 11449356.93 | 100% | 0 | 11449356.93 | Ndokwa East | Complete
149 | 368 | Renovation of 1No. Six Classroom Block with Stores and Toilets at Aboh Secondary School, Aboh, Ndokwa East LGA | 20158343185 | Jane-A-Sons Ventures, Dumebi Street, Asaba | 2019 | 6 Months after award | 21456748.73 | 100% | 0 | 21456748.73 | Ndokwa East | Complete
151 | 490 | Renovation/rehabilitation of 1No.2 classroom block, 1No.3 classroom block, perimeter block wall fence with construction of 2No.gate house and supply of 115 students’ and 18 teachers’ furniture at Isselegu Secondary School, Isselegu, Ndokwa East LGA. | 20158343185 | Ochikap Nig. Enterprises, No.6 Dennis Iyamu Crescent, Off Ibusa Road, Akwuofu, Asaba. | 2019 | 6 Months after award | 49338000 | 100% | 49338000 | 0 | Ndokwa East | Complete
153 | 368 | Construction of 1No.3 classroom block and supply of 25 pupils’ and 5 teachers’ furniture at Agwete Community Primary School, Agwete, Ndokwa East LGA | 20158343185 | Peptabs Integrated Services, 105, Umuseti Road, Utagba-Ogbe, Kwale | 2019 | 6 Months after award | 17420372 | 0% | 0 | 17420372 | Ndokwa East | On-going
154 | 368 | Construction of 1No. six (6) Classroom Block and Erection of State Government branding uniform project signboard at Ugwa S/S Obodo-Ugwa, Ndokwa West LGA | 20158343185 | Jedmans Nig Ent, 24, Infant Jesus Road, Asaba | 2019 | 6 Months after award | 38315137.09 | 100% | 0 | 38315137.09 | Ndokwa West | Complete
155 | 368 | Construction of Administrative Block at Ugwa S/S Obodo-Ugwa, Ndokwa West LGA | 20158343185 | Nwaokom Enterprises, 6, H.P. Otukwueku Street, Asaba | 2019 | 6 Months after award | 25146481.29 | 90% | 5270697.96 | 19875783.33 | Ndokwa West | On-going
157 | 368 | Construction of a prototype 1No. Six (6) classroom block with stores and toilet facilities and Erection of Standard school sign post (with the name of the school and the new State Government logo) at Ugwa S/S Obodo-Ugwa, Ndokwa West LGA | 20158343185 | Innapo Ventures, 17, Gbenga Street, Agbor | 2019 | 6 Months after award | 38410137.09 | 100% | 36228380.24 | 2181756.85 | Ndokwa West | Complete
159 | 490 | Renovation/rehabilitation of 1No.12 classroom block (U-Shaped), 1No.6 classroom block with an attached office and supply of 20 students’ furniture to Umai Primary School, Abbi, Ndokwa West LGA. | 20158343185 | Ernest Sons and Daughters Ventures, 29, Umusam Road, Kwale. | 2019 | 6 Months after award | 49725104.07 | 0% | 0 | 49725104.07 | Ndokwa West | On-going
160 | 490 | Renovation/Rehabilitation of 1No. 6 Classroom Block with offices and toilet facilities at Isumpe Mixed Secondary School, Ulogwe Isumpe and Supply of 185 Students and 20 teachers furniture to selected schools in Ndokwa West LGA | 20158343185 | Nibveb Contractors 14, Bola Ogunsanya Crescent, Magodo, GRA. Lagos | 2019 | 6 Months after award | 39992798.9 | 0% | 0 | 39992798.9 | Ndokwa West | On-going
162 | 368 | i. Supply of 100 Students’ and 20 Teachers’ Furniture at Ogoni Primary School, Aghalokpe, okpe LGA ii. Supply 200 Students’ and 25 Teachers’ Furniture and Erection of Standard School Sign Post (with the name of the School and the new State Logo) at Orerokpe Secondary School, Orerokpe, Okpe LGA. | 20158343185 | Desco Nigeria Enterprises, 71, DLA Road, Asaba | 2019 | 6 Months after award | 13426700 | 100% | 12350000 | 1076700 | Okpe | Complete
166 | 368 | Renovation of 1No. three (3) Classroom Block at Ogoni Primary School, Aghalokpe, Okpe LGA | 20158343185 | Emimarvis Global Resources, 22, Redeemers Street, Asaba | 2019 | 6 Months after award | 11563767.56 | 100% | 10985579 | 578188.56 | Okpe | Complete
169 | 538 | Construction of perimeter fencing of 821m with one gate and security house at Osubi Secondary School, Osubi, Okpe LGA. | 20158343185 | Danike Global Resources Venture No. 71, Textile Mill Road, Benin City | 2019 | 6 Months after award | 49521140.05 | 60% | 32978742.49 | 16542397.56 | Okpe | On-going
174 | 490 | Construction of 1No. Prototype 6 classroom block with offices, Pupils Toilet with Water Stanchion and Borehole (Prototype) and Supply of 50 pupils and 15 Teachers Furniture at Ugbokodo Primary School, Ugbokodo, Okpe LGA. | 20158343185 | Temiko Global Resources 7, Belefia Crescent off Esiri Avenue, Ugbeyiyi | 2019 | 6 Months after award | 49200000 | 0% | 0 | 49200000 | Okpe | On-going
175 | 368 | Construction of 6 classroom block with stores and toilet facilities and Erection of Standard school signboard (with the name of the School and the new State Government logo) at Achalla Mixed Secondary School, Achalla-Ibusa, Oshimili North LGA | 20158343185 | Donnie Brasco & Co Ent. Block 67 DDPA Housing Estate, Opp. Police Headquarters, Asaba. | 2019 | 6 Months after award | 38410137.09 | 40% | 0 | 38410137.09 | Oshimili North | On-going
177 | 368 | Construction of 1No. Six (6) Classroom block with stores and toilet facilities and Erection of State Government uniform branded logo at Ebu Grammar School, Ebu, Oshimili North LGA | 20158343185 | Onye Contracts & Trading Enterprises, 55, Ifeanyichukwu Street, Opp. Infant Jesus School, Asaba | 2019 | 6 Months after award | 38315137.09 | 100% | 9602534.27 | 28712602.82 | Oshimili North | Complete
178 | 368 | Construction of Administrative Block and Staff Room at Ebu Grammar School, Ebu, Oshimili North LGA | 20158343185 | Ecstacy Ventures, 224, Nnebisi Road, Asaba | 2019 | 6 Months after award | 25146481.29 | 50% | 0 | 25146481.29 | Oshimili North | On-going
179 | 368 | Construction of 1No. Six (6) Classroom block with stores and toilet facilities and Erection of School signboard with new State Government Logo at Ebu Grammar School, Ebu, Oshimili North LGA | 20158343185 | Dicksino Nigeria Enterprises, 1, Ndobu Street, Boji-Boji, Owa | 2019 | 6 Months after award | 38410137.09 | 100% | 34397688.49 | 4012448.6 | Oshimili North | Complete
180 | 368 | Supply of 200 students’ desk and 50 teachers’ furniture at Ebu Grammar School, Ebu, Oshimili North LGA | 20158343185 | Neiyadein and Sons Enterprises, No.281 Warri Sapele Road, Warri | 2019 | 6 Months after award | 9730800 | 100% | 0 | 9730800 | Oshimili North | Complete
181 | 368 | Additional works for the renovation of Block wall fence and construction of gate house at Akwukwu-Igbo Grammar School, Akwukwu-Igbo, Oshimili North LGA | 20158343185 | Rawds and Steel Enterprise, No. 19, Burutu | 2019 | 6 Months after award | 1541032.42 | 100% | 0 | 1541032.42 | Oshimili North | Complete
182 | 368 | Construction of a prototype 1No. six (6) classroom block with stores and toilet facilities and Erection of State Government branding uniform project signboard at Achalla Mixed Secondary School, Achalla-Ibusa, Oshimili North LGA | 20158343185 | Nirvana Ventures, 4, House of Assembly Service Commission Road, DDPA, Asaba | 2019 | 6 Months after award | 38315137.09 | 80% | 0 | 38315137.09 | Oshimili North | On-going
183 | 368 | Supply of 300 Students’ and 27 Teachers’ Furniture to Achalla Mixed Secondary School, Oshimili North LGA | 20158343185 | Thixo Affairs Enterprises,8, Otuogwu Street, Asaba | 2019 | 6 Months after award | 12277980 | 100% | 0 | 12277980 | Oshimili North | Complete
184 | 368 | Construction of Administrative Block and Staff Room at Achalla Mixed Secondary School, Achalla-Ibusa, Oshimili North LGA | 20158343185 | Kainene Olisa Services, Isikisi Road, Ibusa | 2019 | 6 Months after award | 25146481.29 | 70% | 6286620.32 | 18859860.97 | Oshimili North | On-going
186 | 49 | Supply of 110 students’ double seater desks and 20 teachers’ furniture at Ugbolu Primary School II, Ugbolu, Oshimili North LGA | 20158343185 | Je-Dor Ent. 17, Okey Anayo Drive, DLA Road, Asaba | 2019 | 6 Months after award | 4987440 | 100% | 0 | 4987440 | Oshimili North | Complete
187 | 490 | Construction of fence and gate house, furnishing of chemistry and physics laboratories, supply of laboratory equipment and instructional materials at Oruchi Comprehensive Secondary School, Okpanam, Oshimili North LGA. | 20158343185 | Deghexon Ventures, 1, Lord Vine Close, DLA Road, Asaba. | 2019 | 6 Months after award | 49498690 | 80% | 25146481.29 | 24352208.71 | Oshimili North | On-going
188 | 490 | i. Demolition and Reconstruction of 1No. 3 Classroom block and Construction of 1No. Prototype Students Toilets with water stanchion and borehole at Okpu-Elechele Primary School and ii. Construction of 1No. Prototype Students toilet with water stanchion and borehole at Oko Mixed Secondary School, Oko and Supply of 50 Students and 5 Teachers Furniture to Okpu-Elechele and Oko Mixed Secondary School, Oshimili South LGA | 20158343185 | AK Leso Ventures Nigeria Plot 4 Mure Close, Opp. UBA, Warri | 2019 | 6 Months after award | 39376780.79 | 90% | 9844195.2 | 29532585.59 | Oshimili South | On-going
189 | 49 | Construction of 1 No. 6 classroom block with stores and toilet facilities and maintenance and improvement of stanchion and tank capacity and construction of 0.4km 50mm UPVC pipeline extension at Government Model College, GRA, Asaba, Oshimili South LGA | 20158343185 | Graphsoft Design Consult, C.B.C. 1 (Block Industry) along Anwai Road, Asaba. | 2019 | 6 Months after award | 39896617.09 | 65% | 9849154.27 | 30047462.82 | Oshimili South | On-going
190 | 368 | Supply of 193 students’ and 25 teachers’ furniture at Government Model College, GRA, Asaba, Oshimili South LGA | 20158343185 | Chovis Multi Links, 2, Olatunji Street, Lagos | 2019 | 6 Months after award | 8260272 | 100% | 2065068 | 6195204 | Oshimili South | Complete
192 | 490 | Renovation of 1No.6 classroom block (B) with offices and 1No.6 classroom block (C) with offices at Okwe Secondary School, Okwe-Asaba, Oshimili South LGA. | 20158343185 | Omitelojor Ventures, 22, Redeemers Street, off Marian Babangida Road, Asaba | 2019 | 6 Months after award | 49219495.16 | 90% | 12099153.05 | 37120342.11 | Oshimili South | On-going
193 | 47 | Construction of prototype 6 classroom block with offices at Afadia College, Asaba, Oshimili South LGA | 20158343185 | Zuru-Elohor Enterprises, 46, Efeizomor Street, Boji Boji Owa | 2019 | 6 Months after award | 34983968.67 | 100% | 8745992.17 | 26237976.5 | Oshimili South | Complete
195 | 47 | Renovation of 1No.6 classroom block with offices and toilets and conversion of an audit building to administrative building at Isioma Onyeobi College, Asaba, Oshimili South LGA. | 20158343185 | Desco Nigeria Enterprises, No.109 Dennis Osadebey Way, Asaba. | 2019 | 6 Months after award | 49785236.19 | 90% | 12446309.05 | 37338927.14 | Oshimili South | On-going
196 | 368 | Supply of 250 Students’/pupils’ double desks and 80 Teachers’ Furniture to Selected schools, Patani | 20158343185 | Royal Lead Properties, 1, Abiodun Street, Ogba, Ikeja, Lagos | 2019 | 6 Months after award | 13255000 | 0% | 0 | 13255000 | Patani | On-going
197 | 549 | Renovation of 6 classroom block without stores/offices, supply of 50 teachers’ and 345 students’ furniture to selected schools in and erection of standard school sign post (with the name of the school and the new State logo) at Anyima Primary School, Abari, Patani | 20158343185 | Nirvana Ventures, 4, House of Assembly Service Commission Road, DDPA, Asaba | 2019 | 6 Months after award | 34087602.45 | 100% | 24900000 | 9187602.45 | Patani | Complete
199 | 549 | Renovation of 1No.3 Classroom Block with offices, construction of student toilets, borehole and stanchion and erection of school sign post with new Delta State Logo at Uduophori Secondary Commercial School, Uduophori, Patani | 20158343185 | De Mustard Seed System services 2 Infant Academy Road, Off Anwai road, Asaba | 2019 | 6 Months after award | 25752089.8 | 30% | 0 | 25752089.8 | Patani | On-going
201 | 549 | Construction of prototype 1No.6 classroom block with offices (but no toilets) at Uduophori Secondary Commercial School, Uduophori, Patani LGA. | 20158343185 | Phigodspily Ventures, 6, Uloho Avenue, Ughelli | 2019 | 6 Months after award | 34983968.67 | 30% | 0 | 34983968.67 | Patani | On-going
203 | 536 | Substitution of the renovation of 1No.6 classroom block with offices and Separate toilet block at Ethiope Primary School, Amukpe with the renovation of a 6 classroom block and the construction of a block of 4 toilets at Okokporo Primary School, Okegborede in Sapele Constituency. | 20158343185 | J-Hova World Enterprises, No.8 Otuogwu Street, Asaba | 2019 | 6 Months after award | 22171963.23 | 60% | 5542990.81 | 16628972.42 | Sapele | On-going
205 | 490 | Construction of 1No.6 classroom block with offices (prototype) and renovation/rehabilitation of 1No.4 classroom block with offices at Ethiope Mixed Secondary School, Sapele, Sapele LGA. | 20158343185 | Gralex Company Nigeria 15, Low Cost Road, Ughelli | 2019 | 6 Months after award | 49400000 | 100% | 12350000 | 37050000 | Sapele | Complete
206 | 490 | Renovation/rehabilitation of 1No.4 classroom block, 1No.6 classroom block with stores and supply of 111 students’ and 13 teachers’ furniture at Okotie-Eboh Primary School, Sapele | 20158343185 | Omitelojor Ventures, 22, Redeemers Street, off Marian Babangida Road, Asaba | 2019 | 6 Months after award | 39503295.38 | 20% | 0 | 39503295.38 | Sapele | On-going
207 | 368 | Construction of a Block of six classroom with one office and Erection of Standard school signboard (with the name of the School and the new State Government logo) at Ugbisi Primary School, Ugbisi, Udu LGA | 20158343185 | Onye Contracts & Trading Enterprises, 55, Ifeanyichukwu Street, Opp. Infant Jesus School, Asaba | 2019 | 6 Months after award | 38410137.09 | 100% | 36228380.26 | 2181756.83 | Udu | Complete
208 | 368 | Construction of Single Tank water Borehole at Ugbisi Primary School, Ugbisi, Udu LGA | 20158343185 | Onye Contracts & Trading Enterprises, 55, Ifeanyichukwu Street, Opp. Infant Jesus School, Asaba | 2019 | 6 Months after award | 2050000 | 100% | 1947500 | 102500 | Udu | Complete
209 | 368 | Renovation of 1No. Five Classroom Block with stores and toilets and Erection of State Government Branding Uniform Project sign post at Ugbisi Primary School, Ugbisi, Udu LGA | 20158343185 | Onye Contracts & Trading Enterprises, 55, Ifeanyichukwu Street, Opp. Infant Jesus School, Asaba | 2019 | 6 Months after award | 16141222.46 | 100% | 15006307.51 | 1134914.95 | Udu | Complete
210 | 368 | Construction of Perimeter Block wall Fence and Toilet block at Ugbisi Primary School, Ugbisi, Udu LGA | 20158343185 | Onye Contracts & Trading Enterprises, 55, Ifeanyichukwu Street, Opp. Infant Jesus School, Asaba | 2019 | 6 Months after award | 15814810.47 | 100% | 14894590.71 | 920219.76 | Udu | Complete
211 | 368 | Supply of 150 Students’ and 20 Teachers’ Furniture at Ugbisi Primary School, Ugbisi, Udu LGA | 20158343185 | Onye Contracts & Trading Enterprises, 55, Ifeanyichukwu Street, Opp. Infant Jesus School, Asaba | 2019 | 6 Months after award | 6458400 | 100% | 6458400 | 0 | Udu | Complete
215 | 490 | Construction of block wall fence and gate house, conversion of 1No.6 classroom block to 1No. 12 classroom and supply of 110 students’ and 21 teachers’ furniture at Owhase Primary School, Owhase, Udu LGA. | 20158343185 | Desco Nigeria Enterprises, No.109 Dennis Osadebey Way, Asaba. | 2019 | 6 Months after award | 49400000 | 100% | 46930000 | 2470000 | Udu | Complete
217 | 368 | Renovation of 1No.6 classroom block and erection of school signpost at Ovwian Primary School, Ovwian, Udu LGA. | 20158343185 | Kodet Global Ventures,12, Iyeghe Street, Aladja, Udu | 2019 | 6 Months after award | 20765926.4 | 100% | 20765926.4 | 0 | Udu | Complete
219 | 368 | Construction of 1No.6 classroom block at Ogbe-Udu Secondary School, Ogbe-Udu, Udu LGA | 20158343185 | Rizim Resources 2, Iloba Ogbotobo Crescent off Nnebisi Road, Asaba | 2019 | 6 Months after award | 35071645.87 | 80% | 0 | 35071645.87 | Udu | On-going
220 | 368 | Demolition and reconstruction of 1No. Principal’s quarters and 1No. Boys’ quarters at Owhrode Secondary School, Owhrode, Udu LGA | 20158343185 | Vovi International Company No. 1, Anwai/Illah Road, Opposite Govt House, Asaba. | 2019 | 6 Months after award | 19480890.53 | 100% | 4807222.63 | 14673667.9 | Udu | Complete
221 | 368 | Construction of 6 classroom block with stores, toilet facilities, supply of 20 teachers’ and 260 students’ furniture and erection of standard school sign post (with the name of the school and the new State logo) at Emeragha Secondary School, Emeragha, Ughelli North LGA | 20158343185 | Ve-Man Global Enterprises, 104, Okpanam Road, Asaba. | 2019 | 6 Months after award | 48873177.09 | 100% | 0 | 48873177.09 | Ughelli North | Complete
224 | 490 | Renovation of 4No. 3 bedroom bungalows at Government College, Ughelli, Ughelli North LGA | 20158343185 | Onye Contracts & Trading Enterprises, 55, Ifeanyichukwu Street, Opp. Infant Jesus School, Asaba | 2019 | 6 Months after award | 44343513.8 | 100% | 0 | 44343513.8 | Ughelli North | Complete
225 | 490 | Renovation of 1No. 3 bedroom bungalows at Government College, Ughelli, Ughelli North LGA | 20158343185 | Gralex Company Nigeria, 15, Low Cost Road, Ughelli | 2019 | 6 Months after award | 11085878.45 | 100% | 10327459.62 | 758418.83 | Ughelli North | Complete
226 | 368 | Alteration /Rehabilitation of woodwork workshop II at Government College, Ughelli, Ughelli North LGA | 20158343185 | FOAC Trust Ventures, 1, Akpoyibo Close, Makolomi, Ughelli | 2019 | 6 Months after award | 18459169.15 | 100% | 17535726.19 | 923442.96 | Ughelli North | Complete
227 | 368 | Alteration/Renovation of Agbarho and Obiaruku hostels at Government College, Ughelli, Ughelli North LGA | 20158343185 | Nirvana Ventures, 6B, HASL Road, Asaba. | 2019 | 6 Months after award | 41788783.61 | 25% | 10447195 | 31341588.61 | Ughelli North | On-going
228 | 368 | Construction of a prototype 1 No. 6 classroom block with stores and toilet facilities at Government College, Ughelli, Ughelli North LGA | 20158343185 | Charleson Industrial Supplies, 68, Portharcourt Road, Osha | 2019 | 6 Months after award | 38135137.09 | 45% | 0 | 38135137.09 | Ughelli North | On-going
230 | 368 | Renovation of 1No.6 classroom block with attached office at Izeze Primary School, Uwheru, Ughelli North LGA. | 20158343185 | Austimoore Enterprises, No.11 Owa Eke Road, Agbor. | 2019 | 6 Months after award | 22757790.36 | 65% | 0 | 22757790.36 | Ughelli North | On-going
231 | 368 | Demolition/reconstruction of 1No.3 classroom block at Izeze Primary School, Uwheru, Ughelli North LGA. | 20158343185 | Brayl Projects and Associates, No. 30 Kotie Street, Okumagba Layout, Warri. | 2019 | 6 Months after award | 14149512.09 | 50% | 3537378.02 | 10612134.07 | Ughelli North | On-going
234 | 490 | i. Renovation/rehabilitation of 1No.3 classroom block with offices and toilet facilities at Oghara Secondary School, Oghara, Agbarha-Otor, 1No.5 classroom block with stores at ii. Emonu Comprehensive Secondary School, Emonu-Orogun and supply of 200 students and 25 teachers’ furniture to Oghara Secondary School and Emonu Comprehensive Secondary School, Emonu-Orogun, Ughelli North LGA. | 20158343185 | Dibo Dolor Nigeria Enterprises, 10, Akponana Street, off Ihwrekpokpor Road, Ughelli. | 2019 | 6 Months after award | 48900000 | 100% | 12225000 | 36675000 | Ughelli North | Complete
235 | 177 | Construction of 1No. Administrative block at Udovie Secondary School, Udovie, Ughelli North LGA | 20158343185 | Complete Office Ventures, No.230, Nnebisi Road, Konwea Plaza, Asaba. | 2019 | 6 Months after award | 25146481.29 | 100% | 0 | 25146481.29 | Ughelli North | Complete
237 | 368 | Renovation of 1No.4 classroom block with offices (former hostel block), 1No.5 classroom block with offices (science block) and 1No.4 classroom block with offices (ICT block) at Unity Model School, Agbarho, Ughelli North LGA. | 20158343185 | Fenmak & Company, 24 Memeh Street, Boji Boji Owa. | 2019 | 6 Months after award | 49174313.03 | 0% | 0 | 49174313.03 | Ughelli North | On-going
238 | 368 | Upward review for the construction of a prototype 1No.6 classroom block with stores and toilet facilities and supply of 50 students’ and 12 teachers’ furniture at Omosuomo Secondary School, Omosuomo, Ughelli South LGA | 20158343185 | Oketex Integrated Ventures, 8, Odogun Avenue, Off Jakpa Road, Effurun. | 2019 | 6 Months after award | 50456423.75 | 80% | 10135884.27 | 40320539.48 | Ughelli South | On-going
240 |  | Substitution of the supply of furniture with the renovation of the floors of 2No.6 classroom block in the award of contract for Construction of administrative block and supply of 289 students’ and 60 teachers’ furniture at Owhawha Secondary School, Otor-Owhawha, Ughelli South LGA | 20158343185 | Kika Dan Global Ventures | 2019 | 6 Months after award | 39759911.32 | 100% | 33942345.72 | 5817565.6 | Ughelli South | Complete
241 | 47 | Renovation of 1No. 2 classroom block, Supply of 200 Students and 20 Teachers Furniture and Erection of School Sign Post with new Delta State Govt. Logo at Asamana Primary School, Arhavwarien, Ughelli South LGA | 20158343185 | Emimarvis Global Resources, Suit 11 & 12 Jamat Plaza, Infant Jesus Road, Asaba | 2019 | 6 Months after award | 20031917.36 | 100% | 5007929.34 | 15023988.02 | Ughelli South | Complete
243 | 549 | Construction of Science Laboratory and Examination Hall at Ughevwughe Secondary School, Ughevwughe, Ughelli South LGA | 20158343185 | Rizim Resources, 2. Iloba Ogbotobo Crescent off Nnebisi Road, Asaba | 2019 | 6 Months after award | 52814246.37 | 95% | 0 | 52814246.37 | Ughelli South | On-going
245 | 490 | Construction of 1No. prototype 6 classroom block with offices and demolition/reconstruction of 1No.3 classroom block with offices at Ofrukama Primary School, Ofrukama, Ughelli South LGA | 20158343185 | Etaga and Sons (Nig) Company Ughelli. | 2019 | 6 Months after award | 48566850.46 | 60% | 12141712.62 | 36425137.84 | Ughelli South | On-going
246 | 490 | Renovation/rehabilitation of 1No.4 laboratory block with concrete work top, offices and toilet facilities at Okpare Grammar School, Okpare-Olomu, Ughelli South LGA | 20158343185 | Emimarvis Global Resources, 22, Redeemers Street, Asaba | 2019 | 6 Months after award | 39507063.73 | 0% | 0 | 39507063.73 | Ughelli South | On-going
247 | 368 | Construction of Administrative Block and Erection of State Government branding uniform project signboard at Obi-Obeti Secondary School, Obi-Obeti, Ukwuani LGA | 20158343185 | Multi-Skills and Trade Enterprises, 10B Nneamaka Close, West End, Asaba | 2019 | 6 Months after award | 25326481.29 | 40% | 0 | 25326481.29 | Ukwuani | On-going
248 | 368 | Supply of 300 Students’ and 27 Teachers’ Furniture at Obi-Obeti Secondary School, Obi-Obeti, Ukwuani LGA | 20158343185 | Classique Oil & Gas Ventures, 10, Nneamaka Close, Opp. FMC, Asaba | 2019 | 6 Months after award | 12277980 | 95% | 6331370.32 | 5946609.68 | Ukwuani | On-going
252 | 49 | Supply of 450 Students’ and 100 Teachers’ Furniture to Selected Schools, Uvwie LGA | 20158343185 | Emimarvis Global Resources, 22, Redeemers Street, Asaba | 2019 | 6 Months after award | 21681000 | 100% | 21681000 | 0 | Uvwie | Complete
254 | 490 | Construction of Corpers’ lodge and supply of 115 students’ and 20 teachers’ furniture at Adult Literacy Centre, Ekpan, Uvwie LGA | 20158343185 | Brytex Precision Services, No.19 Ovwori Str., Ekpan. | 2019 | 6 Months after award | 46375168 | 0% | 0 | 46375168 | Uvwie | On-going
255 | 47 | Construction of prototype 1No. 6 Classroom block with stores and toilet facilities at Iterigbe Secondary School, Uvwie | 20158343185 | Eric Kings Ventures No. 21 Omi Str., Owa-Alero | 2019 | 6 Months after award | 38135137.09 | 5% | 0 | 38135137.09 | Uvwie | On-going
256 | 177 | Construction of 1No.prototype 6 classroom block at Abe I Secondary School, Aruakpor Umah, Uvwie | 20158343185 | Vetic Nig. Enterprise 12, Onyekosor Street, off Marble Hill Scxhool Road, Okpanam. | 2019 | 6 Months after award | 43648963.84 | 35% | 10192240.96 | 33456722.88 | Uvwie | On-going
257 | 47 | Construction of prototype administrative block (small size) at Iterigbe Secondary School, Uvwie LGA | 20158343185 | Triple D Resources, 6, Onyeogali Ukwamedua Street, Okpanam Road, Asaba. | 2019 | 6 Months after award | 15564824.36 | 40% | 0 | 15564824.36 | Uvwie | On-going
258 | 47 | Construction of prototype 1No. 6 Classroom block with stores and toilet facilities at Iterigbe Secondary School, Uvwie LGA | 20158343185 | Farazino Corporate Enterprises, No. 1, Arhiyor Street, Effurun | 2019 | 6 Months after award | 38135137.09 | 60% | 0 | 38135137.09 | Uvwie | On-going
259 | 47 | Construction of prototype students’ toilet and Supply of 300 students’ and 30 teachers’ at Iterigbe Secondary School, Uvwie LGA | 20158343185 | Solo Royal Ventures 61, Convent Street, Boji-Boji, Owa | 2019 | 6 Months after award | 23988734.35 | 40% | 0 | 23988734.35 | Uvwie | On-going
265 | 490 | Renovation of 1No.2 classroom block with office, 1No.6 classroom block with office, 2No.3 classroom block, construction of student toilet with water stanchion and borehole and renovation of 1No. security house at Ajagbodudu Primary School, Ajagbodudu, Warri North LGA | 20158343185 | Alvin-Dennis Consulting, 1, Obiago Close by FMC Roundabout, Asaba | 2019 | 6 Months after award | 49067000 | 50% | 12266750 | 36800250 | Warri North | On-going
266 | 368 | Construction of Prototype 6 classroom block with stores and toilet facilities and Erection of Standard school sign post (with the name of the School and new State Government logo) at Obodo College, Obodo, Warri South LGA | 20158343185 | Danbes Corporate Ventures, 4A Ekpen Street, Okere Market, Warri | 2019 | 6 Months after award | 38410137.09 | 50% | 8516880 | 29893257.09 | Warri South | On-going
268 | 368 | Construction of Administrative Block and Erection of State Government branding uniform project signboard at Obodo College, Obodo, Warri South LGA | 20158343185 | Gehobless Nigeria Enterprises, No. 20, Victory Avenue, Warri | 2019 | 6 Months after award | 25326481.29 | 60% | 10130592 | 15195889.29 | Warri South | On-going
269 | 49 | Construction of 1No. Six (6) Classroom Block with stores and Toilet Facilities at Obodo College, Obodo, Warri South LGA | 20158343185 | Nesfort Vee Ventures, 58, Udogun Avenue, Off Jakpa Road, Effurun | 2019 | 6 Months after award | 38135137.09 | 70% | 26170279.02 | 11964858.07 | Warri South | On-going
270 | 48 | Supply of 400 students’/pupils’ double seater desks and 100 teachers’ furniture to Selected Schools, Warri South LGA | 20158343185 | Ubrete Resources, 6, Chidinma Drive, Asaba | 2019 | 6 Months after award | 19822000 | 100% | 19822000 | 0 | Warri South | Complete
273 | 490 | Conversion of 1No.3 classroom block with offices and toilets to staff quarters and 1No. office block to staff quarters at Ubeji Secondary School, Ubeji, Warri South LGA | 20158343185 | Danbes Corporate Ventures, 4A Ekpen Street, Okere Market, Warri | 2019 | 6 Months after award | 39726234.27 | 50% | 9931558.57 | 29794675.7 | Warri South | On-going
275 | 368 | Supply of 100 students’/pupils’ double seater desks and 30 teachers’ furniture to Selected schools, Warri South West LGA | 20158343185 | Ubrete Resources, 6, Chidinma Drive, Asaba | 2019 | 6 Months after award | 5203000 | 60% | 2081200 | 3121800 | Warri South West | On-going
283 | 368 | Renovation of 1No.8 classroom block with offices and toilets at Isaba Grammar School, Isaba, Warri South West LGA | 20158343185 | Triple D Resources 6, Onyeogali Ukwamedua Street, Okpanam Road, Asaba. | 2019 | 6 Months after award | 39464888.81 | 60% | 9866222.2 | 29598666.61 | Warri South West | On-going
288 | 49 | Supply of 1,102 pupils’/students’ and 200 teachers furniture to Public Primary and Secondary Schools in Delta Central Senatorial District. | 20158343185 | M.O. Adugbo & Sons Ent. Nig 55, Sapele Road, Benin City | 2019 | 6 Months after award | 49947408 | 0% | 0 | 49947408 | Across the State | On-going
290 | 517180013 | Supply of 1,102 pupils’/students’ and 200 teachers furniture to Public Primary and Secondary Schools in Delta South Senatorial District. | 20158343185 | Besa Mercantile Company No. 18 Inalu Street, Umuagu, Asaba | 2019 | 6 Months after award | 49947408 | 0% | 0 | 49947408 | Across the State | On-going
TOTAL | [6 empty] | 5017850999.1 |  | 1358547975.84 | 3659303023.26